CONGLOMERATE IT

Consulting & Delivery

RESPONSE TO REQUEST FOR INFORMATION

Bose Capability Centre (GCC- India): IT, GBS, and R&D Engineering

Submitted to:

BOSE Procurement

Submission Date:

May 21 2026

RFI Reference: India GCC IT & GBS Sourcing Initiative

Primary Contact:

VJ, CEO

vj@conglomerateit.com

THE BLUEPRINT

## Bose Capability Centre India - At a Glance

THE MANDATE Build, operate, and transfer an 800-person India Capability Centre across IT, GBS, and R&D Engineering: designed from Day 1 for Client ownership.

## THE MODEL

| 01 Build-Operate-Transfer Built under our entity. Rebadged to yours at Month 33–36 available from 24th Month. | 02 Cost + ~15% with Open Book (~15% and above) Every cost visible. Every margin defined. Auditable on demand. Would be a point for negotiation. |
| --- | --- |
| 03 Dual-City Footprint Hyderabad for IT and GBS. Bengaluru for R&D. | 04 AI-First from Launch Automation embedded from Day 1, not retrofitted later. |
| 05 Built to Be Inherited Every leader, process, and artifact designed for the day you take full ownership. | 06 Client-Branded from Day 1 Identity, culture, and presence as yours: from the first hire. |

## THE SHAPE WITHIN 2-3 YEARS

| TRACK | HEADCOUNT | SHARE | LOCATION |
| --- | --- | --- | --- |
| R&D Engineering | 320 | 40% | Bengaluru |
| Information Technology | 320 | 40% | Hyderabad |
| Global Business Services | 160 | 20% | Hyderabad |
| TOTAL | 800+ FTE | 100% | Dual-City |

## THE SCALE-UP

| MO 1–3 Mobilize 50 | MO 3–08 Build 200 | MO08–14 Scale 400 | MO 14–19 Scale 650 | MO 19–24 Stabilize 800 | MO 24 –30 Optimize | MO 30 –36 Transfer Rebadge |
| --- | --- | --- | --- | --- | --- | --- |

## THE GOVERNANCE  ·  JOINT OPERATING

| Executive Steering Monthly → Quarterly | Ramp War Room Weekly (first 18 months) | Delivery Governance Weekly / Bi-weekly | Transformation Council Monthly | Transfer Readiness Board Quarterly from Mo 12 |
| --- | --- | --- | --- | --- |

THE GUARANTEE

| I. Transfer Readiness Index Quarterly scorecard from Month 12 across Leadership, Process, Infrastructure, People, Governance, and Commerc1.ial readiness. | II. Executive Access Dedicated SVP as single point of accountability across mobilize, build, scale, transform, and transfer. | III. Open-Book Economics No hidden layers. No surprise mark-ups. Every component visible and auditable on demand. |
| --- | --- | --- |
| “Build for Transfer, Not Dependency.” A capability built for you to own — not for us to retain. |  |  |

- EXECUTIVE SUMMARY

Our Approach to Your Bose Capability Center - India

It is an institution-building mandate, a vehicle for globalization. You are not procuring people; you are commissioning a capability that will, in time, become unambiguously yours.

We recommend a Build-Operate-Transfer model on a Cost + ~15% commercial structure (Cost Plus Pricing Model) with open-book governance, delivered across a dual-city footprint: Hyderabad for IT and Global Business Services, and Bengaluru for R&D Engineering. The full 800-person capability is built under our entity over 36 months and rebadged to your existing Indian entity in the final three months, preserving tenure, benefits, and statutory continuity.

We are suitable for this mandate because our structure delivers what it requires: right-sized accountability in place of layered approvals; direct executive sponsorship in place of account-layer drift; and a commercial discipline built around your eventual ownership rather than our continued retention. Larger providers will offer you a playbook. We offer a partnership: measured quarterly through our Transfer Readiness Index, governed jointly, and auditable on demand.

- SIX LENSES ON THIS MANDATE

## How Our Proposal Speaks to Every Dimension of Your Decision

| I. | The Strategic Lens | “An institution-building mandate, not a staffing engagement: a capability built for you to own, not for us to retain.” |
| --- | --- | --- |
| II. | The Commercial Lens | “Cost + ~15% with open-book. No hidden margins. No surprise mark-ups. Every component visible and auditable.” |
| III. | The Operational Lens | “800 people, three functions, two cities, 36 months: built as one integrated execution engine, stabilised before transfer.” |
| IV. | The Technology Lens | “AI-first from launch: scaling productivity, not just headcount, with Rapid Labs delivering innovation at India cost.” |
| V. | The Governance Lens | “Right-sized accountability with direct executive sponsorship; transfer readiness measured quarterly across six dimensions.” |
| VI. | The Cultural Lens | “Employees identify as yours from Day 1: not at Month 36. The rebadging is administrative; the culture has already shifted.” |

The same conviction runs through every lens: build for transfer, not dependency

| 4.1 | Company Overview, Delivery Capability, and Delivery Model Experience |
| --- | --- |

WHO WE ARE ConglomerateIT is a founder-led global GCC advisory and technology firm. We build Global Capability Centres for enterprises who want to own what they are building: not rent it indefinitely from someone else.

| 2014 Founded | 290+ Global employees | 3 Countries | 4 Office locations | 90 Days to GCC go-live |
| --- | --- | --- | --- | --- |

## Supplier Profile

| Fields | Details |
| --- | --- |
| Legal company name | ConglomerateIT LLC: USA |
| Headquarters | Hyderabad, India (Global HQ) · McKinney & Frisco, Texas, USA (North America HQ) |
| Year established | 2014 |
| Ownership structure | Founder-led private firm. No external investors. No competing client obligations. |
| Total employees globally | 290+ professionals across India and the US |
| India office locations | Hyderabad (primary HQ) · Bengaluru |
| US office locations | McKinney, TX · Frisco, TX |
| Relevant service lines | GCC Advisory & Setup · GCC Transformation · Talent Strategy & Acquisition · AI & Automation Advisory · Data Products · Technology & Global Operations |
| Primary contact (contracts) | Anuradha Warnakulasooriya, Strategy & Operations Anuradha@ConglomerateIT.com · Contracts@ConglomerateIT.com |
| GCC Practice Director: India | Bapu Jee BS, GCC Practice Leader India |
| GCC Advisory Board: India | Dr. Chakravarthy, Advisor & Strategist |
| GCC Advisory Board: USA | S Kumar, GCC Practice Leader USA |
| Academia & Industry Advisor | Dr. Rajanikanth Aluvalu, Leading University India |
| Employer Branding Lead | Sumit Saxena, Digital Director · Ex Publicis |
| GCC Leaders at Conglomerate | Ex TCS, Ex Capgemini, Ex Cognizant, Ex ANSR, Etc., – But runs GCC’ s in a Boutique Way. |

## Service Lines Relevant to this RFI

| Function Area | In-Scope Activities and Capabilities | ConglomerateIT Confirms |
| --- | --- | --- |
| GR&D Engineering | embedded systems, Bluetooth and WiFi-based wireless, low-power, RTOS and Embedded Linux, TinyML, and battery-optimized Al inference, and Mobile App engineering | YES |
| Information Technology | Cloud/DevOps, enterprise applications, data engineering, analytics, cybersecurity/SecOps, IT support operations | YES |
| Global Business Services | Service delivery, service management, PMO, process excellence, reporting, data & analytics and transition management capabilities | YES |

## GCC/BOT/Hybrid/Outsource advisory and setup capabilities

Conglomerate - as a fit for setting up a Global Capability Centre (GCC) for a large enterprise, we differentiate ourselves from a "Capacity" (size) partner to a "Velocity and Precision" partner (specialisation). Large customers often find big Tier-1 vendors too bureaucratic for the agile, high-touch requirements of a new GCC.

## What Sets Us Apart

- Time-to-stand-up: we have operationalized GCCs in 90–120 days using a structured "GCC-in-a-Box" approach, against a Tier-1 norm of 6–9 months

- Senior-led delivery: partner and director-level advisors stay engaged through go-live, not a pyramid that thins out after kickoff

- Talent-led, not template-led: curated hiring for specialist roles (Architects, audio DSP engineers, cybersecurity leads) where Tier-1 batch-hiring models underperform

- Commercial transparency: open-book cost-plus for incubation phases, giving Client full visibility into salaries, real estate, and statutory costs before transfer

## Lifecycle Capability Coverage

- Delivery model strategy and business case (GCC, BOT, hybrid, outsourced, GCaaS / managed captive / hosted GCC)

- India entity operationalization, leveraging Client's existing legal structure where applicable

- City and site selection with proprietary scoring models

- Talent architecture, salary benchmarking, and workforce planning

- Legal, tax, transfer-pricing, and statutory compliance readiness

- Vendor consolidation, incumbent assessment, and rebid strategy

- Operating model and governance design

- Transition planning, knowledge transfer, and hyper care support

- Phase-zero incubation (entity, infrastructure, initial hiring, operations) with clear transfer roadmap for BOT and GCaaS models

| 4.2 | Relevant Experience and Client References |
| --- | --- |

## A. Comparable Engagements

| Client / Sector | Model | Scope | City | Our Role | Outcomes |
| --- | --- | --- | --- | --- | --- |
| EdTech | BOT-to-Captive | IT operations, end-to-end product development, AI-native engineering, executive hiring | Hyderabad | Strategy through BOT transition; designed the captive as AI-native from Day 1 | BOT converted to captive in 12 months. Delivered scope that traditionally requires 200 engineers with a 40-engineer AI-native team, with ~90% of engineering workflows AI-enabled across the organization |
| Global entertainment major | BOT-to-Captive | Content and audience analytics: data engineering, viewer analytics, recommendation/personalization ML, BI | Hyderabad | Strategy through BOT transition; designed analytics operating model, talent architecture, and tooling stack | BOT converted to captive in 12 months; scaled to ~80 analytics engineers; established the client's first dedicated analytics Coe outside HQ, supporting global content and audience decisions |

| 4.3 | Understanding of Client's Challenge |
| --- | --- |

THE MANDATE Client is not evaluating just a cost-reduction exercise. Client is deciding whether to build an institution. 800 professionals. Three functions. Two cities. 24 months. And at the end of it, a capability that is unambiguously yours.

Why India Why Now

|  | What Changed | Why It Matters for Client |
| --- | --- | --- |
| I | Talent ecosystem arrived | Bengaluru now has Harman International, Dolby, Qualcomm QCC, TI audio, and IISc signal processing alumni in one city. The audio DSP and wearable engineering talent Client needs exists in depth, it did not 10 years ago. |
| II | Cost arbitrage is structur | India GR&D engineers cost 65–75% less fully loaded than US equivalents. At 800 people that is not a line item, it is a $60–88M annual saving that compounds. The longer we waits, the more is left on the table. |
| III | The entity is already there | Client holds a 30-year-old India entity, incorporated 1995, Gurgaon. That removes the single biggest barrier to GCC entry: market access. Most firms spend 6 months on what Client has already done. |
| IV | Scale unlocks strategy | 800 people is not a headcount target, it is the threshold where an India operation stops being a cost centre and becomes a capability platform. Engineering CoEs, Control Tower governance, AI-native operations, none of these work at 50 people. |
| V | AI adoption is a now problem | Client's AI adoption is low. India is where that changes fastest. Bengaluru has Google AI, Intel AI labs, and IISc AI research. Hyderabad has Microsoft and Amazon AI. The talent to accelerate Client's AI maturity is not in the US at this price point. |

## Why BOSE is Acting Now and What This Moment Requires

For BOSE, establishing a delivery model in India now is not simply a tactical path to lower operating cost; it is an opportunity to build a more capable, more resilient, and more innovation-led operating model. In our view, this is the right and timely initiative for BOSE, well aligned to where the market is heading and to the capabilities global enterprises now need to build for the future.

Over the next 36 months, success should be measured not only by cost savings, but by how effectively the India organization helps BOSE increase execution speed, improve productivity, and evolve from a support function into a team that takes real ownership of business outcomes, transformation priorities, and innovation delivery.

Talent at Scale: India gives BOSE access to one of the world’s deepest and most scalable talent ecosystems, with more than 2,100 GCCs and 2.3 million professionals. This matters because it enables BOSE to build critical capability faster in areas such as Agentic AI, Machine Learning, Cloud, DevOps, Data, Enterprise Applications, Project / Program Management, Scrum, Product Ownership, Operations, and Digital Engineering—without being constrained by the talent scarcity many other regions face.

Strategic Maturity: For BOSE, the value of India is no longer limited to a traditional "cost-per-seat" equation. The market has matured toward business impact contribution, with 86% of GCCs in India now actively driving global AI/ML charters. This creates the conditions for BOSE to establish a centre that is designed not just to execute tasks, but to own platforms, lead workstreams, and contribute meaningfully to global transformation and innovation agendas.

Regulatory Support: The policy environment also creates a more scalable long-term path for BOSE. The State’s GCC Policy 2024-2029 and India’s Union Budget 2026 provide supportive incentives around cloud investment and offer clearer frameworks for expansion into Tier-2 emerging hubs. For BOSE, this can translate into lower friction, better optionality in location strategy, and a stronger platform for phased expansion over time.

Global Resilience: A broader India footprint can also strengthen BOSE’s resilience. By diversifying operations into India, BOSE can reduce concentration risk, create greater continuity across global delivery, and build a stronger buffer against geopolitical and economic volatility in other regions. In that sense, this move supports not only growth and efficiency but also long-term operating stability.

## When to Keep Captive, When to Transition to India, When to Outsource

Conglomerate's view, grounded in 40+ GBS-inclusive GCC engagements:

- Keep captive (in the U.S.): Roles requiring deep institutional knowledge of BOSE-specific processes not yet documented, or senior stakeholder relationship management that cannot be effectively transitioned in the near term.

- Transition to India GCC: Standardised, high-volume GBS processes: Order Management, Customer Master Data, Operational Procurement, Product Master Data. India provides a huge cost advantage for these roles, with equivalent or better quality when supported by a structured knowledge transfer.

- Outsource: Consider only for non-core, low-differentiation processes where volume does not justify captive investment. Conglomerate's position: outsourcing GBS core should be a last resort, not a default, it surrenders process ownership, data, and institutional knowledge.

## The Five Critical Decisions BOSE Must Make Before Launch

- Purpose – the vision, broader goals and the expected outcomes – KPIs & Governance Model

- Ownership Model - must decide how much control you want from Day 1 versus the speed of entry.

- Location Strategy - selecting the right city balances talent availability, cost, and employee retention.

- Operating Model - which & what combination of GCC, BOT, and partner-supported engagement model with specifics & the vendor consolidation (if any)

- Effective Risk Management – for the parent organisation, must have a plan of action to transition from "Risk Exposure" (during the initial setup phase) to "Risk Resilience" (in the path towards maturity).

Taken together, these five decisions will do more than shape the initial launch model; they will define the quality, resilience, and long-term value of BOSE’s India GCC. In our experience, organizations that align early on purpose, ownership, location, operating model, and risk strategy can move with greater confidence, reduce avoidable execution friction, and build a centre that delivers both near-term efficiency and sustained strategic impact.

Put simply, getting these decisions right at the outset materially increases the likelihood that BOSE’s GCC evolves as intended—from a delivery engine into a true capability and innovation platform.

## Strategic Rationale for the Proposed Model

| Evaluation Metric | Traditional Outsourcing | Pure DIY GCC (In-House) | Conglomerate IT’s Hosted BOT / GCC-as-a-Service |
| --- | --- | --- | --- |
| Time to Market | Fast (1–2 months) | Very Slow (9–12 months) | Fast (3–4 months) |
| IP & Data Control | Low (Shared vendor pool) | Total Control | Total Control (Dedicated, ring-fenced) |
| Culture & Branding | Vendor culture | Client culture | Client Culture (Co-branded workspace) |
| Upfront Capital (CapEx) | Zero | High (Office, tech, legal setup) | Minimal (Operationalized by Conglomerate) |
| Long-Term Asset | No (Vendor owns team) | Yes (Client owns team) | Yes (Client buys out team later) |

Why Traditional Outsourcing & Pure Hybrids Fall Short

Traditional outsourcing and standard hybrid models fail to build long-term enterprise value. They create fragmented delivery, split employee loyalties, and complex IP boundary lines. While they offer speed, they do not allow the US enterprise to build a true, culturally aligned extension of its global team, resulting in higher long-term costs and significant knowledge leakage when vendors rotate staff.

The Bottlenecks of an Immediate DIY GCC

Although the enterprise already possesses a registered Indian entity, activating it into a fully functional technology hub from day one introduces severe operational friction. The enterprise would be forced to divert critical leadership focus toward local real estate procurement, regulatory compliance, statutory benefits administration, and building local HR engines—effectively delaying product roadmaps by 9 to 12 months.

The Hosted BOT Advantage: The Optimal Convergence

The proposed Hosted BOT model eliminates the "speed vs. control" trade-off. It allows the enterprise to immediately leverage our conglomerate’s mature local infrastructure, talent pipelines, and operational scale without large upfront CapEx.

Because the team operates in a dedicated, secure environment on an open-book, ~ 15% cost-plus structure aligned with India's Safe Harbour rules, the enterprise secures total strategic, cultural, and financial control.

This builds a clean, audit-proof operational asset that can be seamlessly migrated onto the enterprise's existing Indian entity the moment local operations mature.

## Operational Balancing Framework (Speed, Control, Compliance, & Scalability)

As an agile ConglomerateIT, our streamlined corporate structure allows us to eliminate the bureaucratic friction typically found in larger vendors. Conglomerate balances the core execution pillars through a highly modular, risk-insulated framework:

- Uncompromised Strategic Control: While employees remain legally on our payroll during the incubator phase, they are structurally and operationally dedicated 100% to your enterprise. The team operates out of a physically ring-fenced, co-branded office bay, uses your internal software deployment tools, and reports directly to your US managers to preserve your engineering culture.

- Audit-Proof Local Compliance: By anchoring our commercial engine to an open-book, 15% cost-plus markup, we strictly align with India's Transfer Pricing Safe Harbour guidelines, guaranteeing a frictionless financial audit trail for your corporate legal team.

- On-Demand Long-Term Scalability: Our model prevents capital lock-in. We scale infrastructure and headcount incrementally based on your product roadmap, avoiding heavy upfront CapEx. When your operations reach maturity, our pre-structured legal transfer framework allows you to seamlessly migrate the entire operational asset directly onto your registered Indian entity without disrupting delivery timelines.

## What success should look like over 12-36 months

In summary, the table reflects a clear maturity path for BOSE’s India GCC: beginning with rapid setup and cost efficiency, progressing into scaled delivery and measurable productivity gains, and then evolving into a centre that builds differentiated capability, leads transformation agendas, and ultimately contributes enterprise-wide value. The broader implication is that success should not be assessed only by early savings, but by how effectively the India organisation matures into a strategic platform for innovation, ownership, and long-term business impact.

| Phase | Timeline | Primary Objective | Key Success Metrics (KPIs) |
| --- | --- | --- | --- |
| Foundation Stage | 0–12 Months | Establish the foundation for cost efficiency and scalable growth | 90-day time-to-market; 100% compliance with local labour and SEZ laws; 30 to 50% cost efficiency (India vs. onshore with Conglomerate) and 20% with Indian Partners Vs Conglomerate |
| Scaled Delivery Stage | 12–18 Months | Scale delivery, strengthen execution, and improve business outcomes | 10-15% delivery / productivity / speed gains via cross-functional pods; high retention of "niche" talent; successful delivery |
| Capability Leadership Stage | 18–36 Months | Build differentiated capability, digital depth, and transformation ownership | Global AI initiatives led from India; creation of reusable intellectual property… An estimated 71% of GCCs use Generative AI across multiple business functions, and 58% are currently investing in Agentic AI. |
| Innovation Ownership Stage | 36-48 Months | Own end-to-end product development, R&D, and creation of new value | Product Developed – Go to Market timelines (1.5 to 2x faster) |
| Strategic Enterprise Impact Stage | 48-60 Months | Drive enterprise-wide impact, global leadership roles, and measurable value contribution | Enterprise wise P&L Contribution (30% to 50% cost efficiency) |

Taken together, this progression reinforces that BOSE’s India GCC should be viewed not as a one-time setup exercise, but as a deliberate capability-building journey. The strongest outcomes will come from treating the centre as a strategic asset that evolves from delivering early efficiency gains into creating differentiated capability, stronger ownership, and measurable enterprise value over time. In that sense, the table is less a timeline of activities and more a roadmap for how BOSE can build a durable platform for growth, innovation, and long-term competitive advantage.

| 4.4 | Recommended Setup Approach and Operating Model |
| --- | --- |

## ConglomerateIT’s Build-Operate-Transfer on Cost Plus Model

The Strategic Challenge

Establishing a high-scale Global Capability Centre (GCC) that unifies Information Technology (IT), Business Global Services (BGS), and Research & Development (R&D) is one of the most powerful strategic moves an international enterprise can make to drive operational efficiency, accelerate execution, and sustain long-term innovation.

However, the traditional standalone (DIY) route often involves significant upfront capital commitments and regulatory lead times of 12 to 18 months, while conventional outsourcing can create unacceptable intellectual property (IP) and control risks. ConglomerateIT’s cost-plus Build-Operate-Transfer (BOT) framework offers an enterprise-grade alternative that enables immediate launch, reduces expansion risk, and preserves strategic control.

The Recommendation: ConglomerateIT's Unified Cost-Plus BOT Model

This model provides BOSE with a unified operating structure through which IT, BGS, and R&D functions can scale concurrently while retaining governance discipline, cost transparency, and decision rights. Under a cost-plus commercial construct, BOSE bears the actual costs with a fixed management fee, creating line-of-sight into the underlying cost base and avoiding the opaque margin structures often embedded in traditional outsourcing arrangements. ConglomerateIT assumes responsibility for the local operating layer—including infrastructure, compliance, and workforce, etc.thereby allowing BOSE to focus on strategic oversight, functional performance, and long-term capability development.

This GCC-as-a-Service model is expected to deliver 40–60% cost savings relative to equivalent home-country operations, while reducing operating costs by ~15–25% compared with a self-managed captive centre or traditional large-vendor outsourcing model in India.

Accordingly, the proposed model may be characterised as a Managed GCC delivered through a Hosted BOT framework. Within this construct, ConglomerateIT would charge a management fee of ~ 15% over the actual cost base, providing a transparent commercial structure that supports local execution, compliance, and operating governance.

| 4.5 | India Location Strategy |
| --- | --- |

In the architecture of a Global Capability Centre (GCC), location selection is no longer a mere real estate or cost-saving decision; it is the single most critical determinant of long-term operational resilience, cultural alignment, and scaling velocity. For a U.S. enterprise looking to expand its footprint, a poorly optimized location strategy introduces immediate bottlenecks—such as hyper-competition for talent, infrastructure constraints, and rising operating overhead—that can degrade product roadmaps and erode the financial advantages of offshoring.

An effective location strategy balances four vital operational pillars to ensure the GCC functions as a high-performing extension of the parent organization.

## ConglomerateIT Location Intelligence, How We Know What We Know

ConglomerateIT’s location assessment is designed to help BOSE make a city choice that supports both immediate launch success and long-term GCC maturity. Our in-house experts maintain quarterly-updated intelligence across all four shortlisted cities, covering talent supply, salary movement, attrition trends, business ecosystem signals, and operating conditions. Importantly, this view is not derived from static market reports alone; it is grounded in live hiring data across active GCC environments and informed by direct engagement with local talent markets, real estate advisors, government bodies, and academic institutions. This gives BOSE a more decision-ready perspective on where the right balance of scale, quality, cost, resilience, and growth potential can be achieved.

Our assessment framework evaluates each city across six critical attributes. Together, these dimensions provide a practical view of whether a location can support BOSE’s ambition not only to launch efficiently, but also to build a sustainable, high-performing, and scalable India organisation over time.

- Talent Pool & Availability – assesses the depth, quality, and accessibility of talent across IT, GBS, and R&D role families. This is the most important variable in determining whether BOSE can ramp at speed, hire niche capability, and sustain growth without being constrained by local talent scarcity.

- Infrastructure & Connectivity – evaluates the reliability of transport networks, airport access, office corridors, digital connectivity, and utility resilience. For BOSE, this directly affects employee commute experience, operating continuity, collaboration with global teams, and the practical ease of scaling a professional delivery environment.

- Government Policies and Incentives – considers the strength of state support, ease of regulatory engagement, and the availability of GCC-friendly incentives, including infrastructure and expansion policies. This matters because a supportive policy environment can reduce friction, improve speed to activation, and create more attractive options for phased expansion over time.

- Cost of Operations – reviews the expected cost base across salaries, real estate, transport, and supporting infrastructure. Rather than looking at cost in isolation, we assess whether the city offers the right cost-to-value equation for BOSE, balancing efficiency with the quality and maturity required for a strategic GCC.

- Quality of Life for Employees – examines the broader employee experience, including livability, commute burden, social infrastructure, and attractiveness to professionals relocating or changing employers. This factor is particularly important for retention, employer brand strength, and BOSE’s ability to position the GCC as a destination for high-quality talent rather than simply a low-cost delivery site.

- Partner and Vendor Ecosystem – evaluates the presence and maturity of supporting partners across recruitment, facilities, compliance, technology services, and specialised delivery needs. A strong local ecosystem provides BOSE with greater execution flexibility, faster problem resolution, and lower operating risk during both setup and scale

Taken together, these six dimensions allow us to move beyond a narrow cost comparison and make a more complete judgment on location suitability. The result is a recommendation that reflects where BOSE is most likely to achieve the strongest combination of launch readiness, talent sustainability, operating efficiency, and long-term strategic value.

## GCC Location Suitability Rating Matrix

This framework scores each city out of 10 across key strategic attributes, mathematically demonstrating why Bengaluru and Hyderabad emerge as the premier choices for a multi-disciplinary (IT, BGS, R&D) centre.

Strategic Location Rating Matrix (Scores out of 10)

| Location Suitability Attribute | Hyderabad (The Balanced Scale Winner) | Bengaluru (The Innovation Anchor) | Pune (The Engineering Hub) | Chennai (The Transaction Anchor) |
| --- | --- | --- | --- | --- |
| 1. Talent Pool Depth (Availability across IT/BGS/R&D) | 9 / 10 (Massive tech/BFSI pool) | 10 / 10 (Deepest tech ecosystem) | 7 / 10 (Niche product focus) | 7 / 10 (Heavy transactional focus) |
| 2. Talent Retention (Lowest attrition risk) | 8 / 10 (Stable, long tenures) | 5 / 10 (High poaching/volatility) | 8 / 10 (Steady employee cycles) | 9 / 10 (Best retention in India) |
| 3. Financial Optimization (Real estate & salary costs) | 9 / 10 (Highly cost-competitive) | 6 / 10 (Premium talent/lease costs) | 8 / 10 (Balanced cost indexing) | 8 / 10 (Highly cost-efficient) |
| 4. Urban Infrastructure (Commute & connectivity predictability) | 9 / 10 (Planned corridors/lower traffic) | 5 / 10 (Severe commute bottlenecks) | 7 / 10 (Manageable traffic/flow) | 8 / 10 (Excellent utility backups) |
| 5. Business Ecosystem Maturity (Global capability presence) | 9 / 10 (Hosts ~17% of India's GCCs) | 10 / 10 (Hosts ~39% of India's GCCs) | 7 / 10 (Strong industrial base) | 8 / 10 (Long-standing MNC base) |
| 6. Boutique Partner Feasibility (Flexibility of Cost-Plus BOT) | 10 / 10 (Maximum ease of operations) | 7 / 10 (High competition from giants) | 8 / 10 (Ideal for targeted teams) | 8 / 10 (Great for large, shared ops) |
| TOTAL SCORE | 54 / 60 (90%) 🏆 | 43 / 60 (71.6%) 🥈 | 45 / 60 (75%) | 48 / 60 (80%) |

- Bengaluru is your "Innovation Anchor": It scores a perfect 10/10 for talent depth and ecosystem maturity. If your centre's absolute priority is recruiting world-leading GenAI/LLM architects instantly, Bengaluru is unmatched, though you must budget for a premium cost structure and higher attrition volatility.

- Hyderabad is your "Operational Sweet Spot": Scoring the highest overall (90%), Hyderabad provides a premium tier-1 talent scale but completely offsets Bengaluru's weaknesses by delivering superior cost optimization, lower attrition, and planned, predictable urban infrastructure.

- The Recommendation: ConglomerateIT suggests establishing your core multi-functional centre in Hyderabad & a mini centre in Bengaluru for R&D and also as BCP / DR site. This allows your Bridge Leaders to maximize delivery velocity, lower your long-term Total Cost of Ownership (TCO), and scale your IT, BGS, and R&D tracks in a highly predictable environment.

## Hyderabad and Bengaluru in Conclusion

In conclusion, Hyderabad and Bengaluru represent the two strongest GCC location choices in India for BOSE’s strategic objectives. While several Indian cities offer pockets of strength, these two locations stand out most clearly when assessed across the factors that matter most for a successful multi-functional GCC: talent depth, scalability, innovation access, operating resilience, ecosystem maturity, and long-term value creation.

- Hyderabad and Bengaluru are the two best choices overall

- Hyderabad is positioned as the strongest primary GCC location

- Bengaluru is positioned as the strongest complementary location for:

- innovation

- R&D depth

- business continuity resilience

| 4.6 | Legal, Tax, and Compliance Readiness |
| --- | --- |

Client's existing India entity is treated as a potential strategic asset, qualified through early-engagement diligence on tax health, statutory standing, and governance maturity. Where the entity is sound, it becomes the receiving vehicle at transition, extended into Karnataka and Telangana as additional locations under the existing PAN, preserving continuity of tax positions, APA coverage, and audit history. Where diligence surfaces material concerns, a new entity is established instead. The build-and-operate phase remains unchanged in either path; only the receiving vehicle changes.

During the operate phase, the GCC runs entirely within our firm's India entity in Hyderabad and Bengaluru. We carry operational, statutory, and people accountability, including all state registrations, SEZ/STPI approvals, incentive applications, labor compliance, and FEMA reporting. Client's existing entity stays insulated from build-phase risk, contracting obligations, and transfer pricing complexity throughout this period.

We recommend contracting through Client's US entity in USD during the operate phase. This structure delivers 3.0–5.7% in tax and regulatory savings through zero-rated GST, no withholding tax, no TP burden on Client, and direct USD repatriation. Permanent Establishment risk if any is structurally manageable through independent contractor framing, controlled US personnel exposure, and contractually clean premises arrangements and evaporates at transition once the workforce moves to Client's entity.

Readiness sequences across four parallel tracks: entity setup and contracting (Months 1–6), talent and operations buildout (Months 3–36), steady-state operations (Months 12–30), and receiving entity readiness with workforce transition design (Months 24–36). The critical window is Months 24–36, where the receiving entity activates state registrations, files fresh SEZ/STPI applications, and prepares to absorb the rebadged workforce with full-service continuity.

Specialist legal, tax, transfer pricing, labor law, and SEZ support is embedded at the moments that matter most, contracting, transition design, and post-transition TP setup. Each workstream interfaces with a defined Client function through a joint Globalization Office with single points of contact on both sides, structured operations reviews, and a dedicated Transition Office activated from Month 24 for rebadging readiness.

The result is a delivery model that gives Client the speed and risk transfer of an externally built capability, while ending with the entity continuity, tax efficiency, and strategic ownership of a directly built one.

Leveraging Client's Existing India Entity

Client's existing India entity is potentially a strategic asset. Our approach qualifies it through diligence, protects it during build and operate phases, and positions it as the receiving vehicle at transition  with a clean fallback to new entity establishment if diligence surfaces material concerns.

Engagement Phases and Approach

| Phase | Role | What Happens |
| --- | --- | --- |
| Foundation | Diligence on Client's existing entity | Established operations, mature compliance infrastructure, banking and tax relationships, and a track record with Indian authorities take years to build and cannot be replicated through new entity creation. We qualify the entity as a strategic asset through structured diligence, not as a default assumption. |
| Two Possible Paths | Receiving vehicle decision | Path A: If diligence confirms the existing entity is sound, it becomes the receiving vehicle at transition. Path B: If diligence surfaces material concerns, we recommend establishing a new entity instead. The build-and-operate phase stays unchanged in either path; only the receiving vehicle changes. |
| Operate Phase | GCC runs within our firm's India entity | This isolates Client's existing entity from build-phase risk, audit exposure, and transfer pricing complexity. We carry operational, statutory, and people accountability. Client's entity remains free of contracting obligations, recharges, and characterization disputes and where diligence supports it, emerges as the receiving vehicle at transition. |
| Pre-Transition | Receiving entity readiness | Path A: Operational extensions into Karnataka and Telangana under the existing PAN/CIN, additional locations, not new incorporations. Preserves continuity of tax positions, audit history, and any existing APA coverage, allowing them to extend cleanly to the new units. This is a structural advantage over new-entity models, where TP characterization, audit history, and APA must be built from scratch. Path B: New entity setup and registrations sequenced during operate phase so it is fully operational by transition. |
| Transition | Workforce rebadging and coordinated handover | The workforce rebadges to the receiving entity with full-service continuity. Real estate, vendor relationships, statutory registrations, and incentive frameworks transition as a coordinated handover. Client emerges with a fully operational two-city GCC, fully integrated into its governance, finance, and tax architecture. |

Path A vs Path B at Transition

The receiving vehicle decision is grounded in diligence, not assumption. The dimensions below frame the trade-off:

| Dimension | Path A:: Existing Entity | Path B:: New Entity |
| --- | --- | --- |
| Receiving vehicle | Client's existing India entity, extended into Karnataka and Telangana | New India entity established during operate phase |
| Registrations approach | Additional locations under existing PAN/CIN | Fresh incorporation and statutory setup |
| Tax positions and APA | Existing positions and APA coverage extend cleanly to new units | TP characterization and APA must be built from scratch |
| Audit history | Continuity preserved across all locations | Fresh slate at new entity |
| When this path is preferred | Existing entity passes diligence on tax health, compliance posture, and governance | Diligence surfaces material concerns that would contaminate new operations |

Outcome

The result is a delivery model that gives Client the speed and risk transfer of an externally-built capability, while ending with the entity continuity, tax efficiency, and strategic ownership of a directly-built one.

Registrations, Permits, Labor-Law, Governance, and Compliance Considerations

Two parallel compliance footprints run through this engagement, one in our firm's entity during operations, and one in the receiving entity ahead of transition.

| Category | During Operate Phase | Pre-Transition (Receiving Entity) |
| --- | --- | --- |
| State Registrations | GST, Shops & Establishments, Professional Tax, Labour Welfare Fund: Karnataka and Telangana | Same registrations under receiving entity, in both states |
| Operational Permits | SEZ or STPI approvals, municipal trade licenses, fire/pollution/safety NOCs | Fresh SEZ/STPI applications unit-specific, not transferable |
| Incentive Registrations | Karnataka GCC Policy, Telangana TS-iPASS | Fresh applications under receiving entity |
| Direct Tax & TP | Corporate tax, statutory audit, TDS compliance | TP framework activation, APA extension or fresh APA strategy |
| Indirect Tax | GST returns, ITC management, intermediary services positioning | GST registration in new states, ITC migration |
| Labor & Employment | EPF, ESI, POSH committees, night-shift permissions, Code on Wages compliance | EPF/ESI extension, contract labour registrations, handbook alignment |
| Foreign Exchange | FEMA reporting, FIRC documentation, AD bank compliance | FLA, FCGPR, FEMA alignment at transition |
| Data Protection | DPDPA 2023, DPO designation, cross-border data flow framework | Data controllership transition to receiving entity |

Labor-law considerations during transition include employee rebadging mechanics, voluntary employee acceptance, continuity of service preservation, PF continuity through UAN-based transfer mechanisms, gratuity transition planning, and applicable transfer-of-undertaking obligations for eligible employee categories.

Governance operates through a joint Globalization Office with single points of contact on both sides. weekly operations reviews, monthly steering, quarterly business reviews with US and India sponsors. A dedicated Transition Office activates ahead of transition for rebadging readiness and statutory handover.

Tax, Transfer-Pricing, and Finance Setup Considerations

During the operate phase, the existing entity carries no incremental tax or compliance burden. our firm holds operational and statutory responsibility. The setup work focuses on preparing the existing entity to absorb the GCC cleanly at transition, with continuity of tax positions, TP framework, and APA coverage where they exist.

| Area | Setup Consideration |
| --- | --- |
| Direct Tax | No incremental tax impact on existing entity during operate phase, it is not the contracting party. Post-transition, existing tax regime continues; concessional rate eligibility under Section 115BAA preserved. |
| Transfer Pricing | Existing entity's TP positions, benchmarking, and APA coverage extend to new Karnataka and Telangana units. Form 3CEB scope expands at transition. Industry markup benchmark for captive engineering/R&D: 15–18%. |
| APA Strategy | If existing APA covers Gurgaon operations, amendment to include new units is the preferred path, preserves rollback and certainty. If no APA exists, transition is the right window to file. |
| Indirect Tax | GST registrations in Karnataka and Telangana under existing PAN. ITC migration planning for assets and operations transitioning at end of term. SEZ/STPI export classification continued under fresh approvals. |
| Asset & Lease Transfer | Lease assignment stamp duty (0.25–1%, ~INR 25–50 lakhs). Asset transfer GST and income tax implications addressed through asset purchase agreement. Slump sale characterization risk mitigated through structuring. |
| Foreign Exchange | FEMA reporting on receiving entity for new locations. FLA filings updated at transition. AD bank relationships extend from existing entity. |
| Finance & Accounting | Existing reporting cadence absorbs new locations at transition. New cost centres in existing accounting system. Statutory audit scope and Internal Financial Controls framework extended. Ind AS / US GAAP / IFRS alignment maintained per current policy. |
| Receiving Entity Health | Diligence on open audits, ongoing TP disputes, regulatory notices, FEMA history, and governance maturity. If material concerns surface, new entity at transition is recommended instead. |

Ownership of Workstreams

Three lanes of accountability run through the engagement, items we own directly, items we coordinate with specialist third parties, and items the Client owns. The transition phase requires the most joint execution; the operate phase is overwhelmingly ours.

| Workstream | Our Firm | Coordinated | Client |
| --- | --- | --- | --- |
| State registrations, SEZ/STPI approvals, real estate, payroll, talent, day-to-day operations (operate phase) | ✓ | • |  |
| Karnataka GCC Policy and Telangana TS-iPASS: incentive applications during operate phase | ✓ | • |  |
| Quarterly governance and steering reviews | ✓ |  | ✓ |
| Receiving entity extension into Karnataka and Telangana |  | • | ✓ |
| Fresh SEZ/STPI applications under receiving entity |  | • | ✓ |
| Real estate lease assignment and stamp duty | ✓ | • | ✓ |
| Employee rebadging: communication, offer letters, acceptance | ✓ | • | ✓ |
| PF (UAN) and gratuity transitions | ✓ | • | ✓ |
| US tax classification (Capex / Opex) and US TP documentation |  | • | ✓ |
| Post-transition TP setup: APA extension, Form 3CEB scope expansion |  | • | ✓ |
| Asset transfer agreement and valuation (if applicable) |  | • | ✓ |

Legend: ✓ = primary ownership;  • = coordination with external specialists (legal, tax, TP, SEZ, valuer, payroll, real estate, EPFO/trust admin).

US Entity vs India Entity Contracting

Recommendation: Contract through Client's US entity, in USD.

This decision shapes how money flows from the US to India during the operate phase, and it has real implications for cost, risk, and complexity. Two paths are possible:

•  Option A: US Entity Contracting: Client's US parent pays our firm directly, in USD, for services delivered in India.

•  Option B: India Entity Contracting: Client's existing India entity pays our firm in INR, then recharges the cost back to the US parent.

Option A is cleaner, cheaper, and lower risk for Client. Here's why.

Why Option A Saves Money

Every step of the payment journey has a tax or compliance friction point. Option A removes most of them.

| Where the friction sits | Option B (India) | Option A (US) | Savings |
| --- | --- | --- | --- |
| GST on our invoices | 18% GST applies; Client gets it back as refund 60–90 days later: but cash is locked in the meantime | Zero-rated as export of services, no GST, no refund cycle | 1.0–1.8% |
| Withholding tax on payments | TDS of 2–10% on every payment; admin and float | No Indian WHT on USD coming in from overseas | 0.3–0.5% |
| Transfer pricing paperwork | Client's India entity must justify the recharge to US parent every year, Form 3CEB, benchmarking studies | Our firm and US parent are unrelated parties, no TP applies during operate phase | 0.2–0.4% |
| TP audit risk | India's tax authority routinely challenges recharge markups; penalties can be 100–300% of disputed tax | Zero exposure for Client during operate phase | 1.0–2.0% |
| Getting money out of India | Eventually has to flow back via dividends, treaty WHT, board approvals, FEMA paperwork | Money never enters India to begin with: paid directly to our USD account | 0.5–1.0% |
| Total |  |  | 3.0–5.7% |

On an 800-FTE engagement, this is meaningful money over three years.

The PE Risk

The legitimate concern with Option A: does paying our firm in USD create a "Permanent Establishment" of the US parent in India? PE is the taxman's way of saying "you effectively have a business presence here, so we'll tax you as if you do." If a PE is found, the US parent could face Indian corporate tax on income attributable to that presence.

Under the India-US tax treaty (Article 5), three things could trigger PE. Each one is structurally manageable:

| What could trigger PE | What it means | How we prevent it |
| --- | --- | --- |
| Service PE | US parent employees spending >90 days in India in any 12-month period | No US parent personnel deployed to our operations. Oversight visits capped at <30 days per individual |
| Agency PE | Our firm acting as an "agent" of US parent, signing contracts on their behalf | We operate as an independent contractor. Explicit no-agency language in the MSA. We serve our broader client portfolio, not just US parent |
| Fixed Place PE | Our office space treated as US parent's office in India | Premises are leased by us, used for our broader operations. No dedicated workspace for US parent personnel |

The one watch item: secondment. If Client wants to send US employees to India for training or transition, this gets legally sensitive. We structure these as formal short-term secondments with cost-to-cost reimbursement, not as part of the engagement scope. India's tax courts have litigated heavily in this area, so the structuring matters.

Importantly, PE risk disappears at transition. Once the workforce moves into Client's India entity, the GCC becomes a standard parent-subsidiary relationship, no different from Client's existing Gurgaon operations today.

Net residual risk during operate phase: low and time-bound (3 years). We document operational autonomy and run quarterly PE-risk reviews to keep the structure defensible.

Sequencing of Readiness Activities

Readiness runs in parallel tracks designed to deliver operational stand-up in months, sustain steady-state delivery, and execute a coordinated transition at end of term. The critical sequencing window is Months 24–36, where the receiving entity readies in parallel with continued operations.

| Phase | Timing | Key Activities |
| --- | --- | --- |
| Entity Setup (Our Firm) | Months 1–4 | State registrations, SEZ/STPI approvals, incentive registrations, real estate, operational readiness review |
| Contracting Foundation | Months 1–6 | MSA with Client's US parent, vendor and subcontractor agreements, incumbent provider transition |
| Talent and Operations Buildout | Months 3–36 | Leadership hires, employee policies, payroll setup, volume ramp across three years |
| Steady State Operations | Months 12–30 | Delivery at scale, governance cadence, incentive capture and disbursement management, risk reviews |
| Receiving Entity Readiness | Months 24–36 | State registrations under Client's entity, MCA disclosures, fresh SEZ/STPI applications, lease assignment design, asset transfer planning |
| Workforce Transition Design | Months 28–34 | Employee communication strategy, offer letters from Client's entity, service continuity confirmation, PF and gratuity transition planning, |
| Transition Execution | Month 36 | Final payroll under our firm, first payroll under Client, lease assignments effective, vendor reassignments, statutory transitions |
| Stabilization | Months 37–42 | Joint operations, knowledge transfer documentation, open issue resolution, disengagement |

Specialist Support and Client Function Interface

Specialist legal, tax, and transfer-pricing support runs across the engagement, with engagement-grade specialists embedded at the moments that matter most, contracting, transition design, and post-transition TP setup. Each workstream interfaces with a defined Client function through the joint Globalization Office.

| Workstream | Specialist Required | Client Function Interface |
| --- | --- | --- |
| MSA negotiation with Client's US parent | Corporate counsel (both sides) | Client Legal: joint negotiation |
| Direct tax structuring and entity tax positions | Big 4 tax advisor | Client Tax + US Tax: joint design at transition |
| Transfer pricing: APA extension, benchmarking, Form 3CEB | TP specialist (Big 4 or boutique) | Client Tax + US TP advisor: joint |
| Indirect tax and intermediary services positioning | GST/indirect tax counsel | Client Tax |
| SEZ/STPI approvals (the Client's) | SEZ specialist consultant | Client Finance: quarterly status |
| Labor law and rebadging mechanics | Labor law counsel | Client HR + Legal: critical at Months 24–36 |
| Real estate, lease assignment, stamp duty | Property counsel + RE advisor | Client Procurement + Finance |
| Data protection (DPDPA 2023, cross-border data flow) | Privacy counsel | Client Legal + Privacy Office |
| Gratuity trust transition and actuarial work | Actuarial advisor + trust admin | Client HR + Finance |
| Asset valuation (if assets transfer) | Registered valuer | Client Finance + Procurement |
| US tax: Capex/Opex classification of setup spend | Client's existing CPA | Client Finance + Tax |

Governance Model

Engagement governance operates through a joint Globalization Office with single points of contact on both sides weekly operations reviews, monthly steering committee, quarterly business reviews with US and India executive sponsors. A dedicated Transition Office activates from Month 24 to focus exclusively on rebadging readiness, statutory handovers, and receiving entity preparation.

| 4.7 | Operating Model and Governance |
| --- | --- |

- Financial Flow: Cost + Management Fee to ConglomerateIT.

- Employment & Payroll: ConglomerateIT hires the talent under its own legal name and pays their salaries and statutory benefits.

- Operations: ConglomerateIT manages the office, IT infrastructure, and local Indian compliance.

- Output: The talent works directly for the customer, ensuring all Intellectual Property (IP) flows back to the BOSE.

What This Approach Allows BOSE to Achieve

- 100% Financial Transparency: Every single expense—from individual engineer salaries to office utility bills—is billed at verified actual cost, eliminating hidden vendor margins.

- Reduced Initial Capital Expenditure (CapEx): The client builds a highly functional offshore division without spending capital on foreign corporate entity registrations, legal setup fees, or long-term commercial lease liabilities.

- Direct Strategic Control: While ConglomerateIT acts as the local operational employer, the client maintains 100% direct control over recruitment benchmarks, engineering standards, sprints, and team culture.

- On-Demand Audit Rights: The client retains the contractual right to review payroll slips, utility bills, and vendor receipts quarterly, ensuring deep executive trust and open-book compliance.

- Ironclad Intellectual Property Vesting: Because all direct technology and workspace infrastructure are mapped to the client, 100% of the generated source code, automated workflows, and data pipelines vest with the client from the moment of creation.

- Bespoke Scalability: The cost structure is completely modular. As the client's team expands or contracts, the invoice scales linearly based on precise per-employee and per-seat actual costs, plus a predictable, fixed percentage markup.

## Why ConglomerateIT is Uniquely Positioned

ConglomerateIT is a premium, agile technology services firm engineered to deliver high-touch operational solutions. We represent the next evolution of Global Capability Centre (GCC) enablement: a boutique, hyper-focused partner powered by an elite task force of industry veterans.

While this deployment marks ConglomerateIT’s inaugural institutional multi-disciplinary GCC framework, our operational delivery model is backed by an assembled ecosystem of experts possessing decades of individual enterprise scaling experience across IT infrastructure, Global Business Services (BGS), and deep-tech Research & Development (R&D).

At ConglomerateIT, we understand that establishing a multi-functional Global Capability Centre (GCC) is a high-stakes strategic move. Because we are an agile, boutique firm, we do not expect you to rely blindly on corporate history. Instead, we have engineered an institutional-grade framework designed to earn your trust through total transparency, elite expert backing, and a zero-risk incubation model.

## The ConglomerateIT Commitment: 6 Pillars of Execution Certainty

- Direct Principal Governance: Our founders personally oversee your account daily, completely bypassing vendor bureaucracy.

- Bespoke Customization: We adapt all physical layouts, network controls, and workflows to match your exact global corporate standard.

- Assembled Advisory Taskforce: Your centre is deployed by handpicked, elite industry veterans leading our real estate, compliance, and engineering tracks.

- Zero-CapEx Proof of Concept: Launch your initial cohorts inside our active office with absolutely zero upfront infrastructure risk.

- Performance Skin in the Game: We tie a portion of our management markup directly to meeting explicit, milestone-driven KPIs.

- Open-Book Financial Dashboard: We provide real-time, digital, line-item visibility into every operational expense.

## Core Delivery Framework: Built for Executive Trust

- The Boutique Partnership Advantage

Choosing ConglomerateIT ensures your GCC is our top corporate priority. Your centre will never be handed down to a junior account manager. We provide Direct Principal Governance, meaning our founders and executive leadership personally handle daily oversight, risk mitigation, and strategic coordination. This agility enables Bespoke Customization, allowing us to instantly pivot workflows, adjust cost structures, or customize the physical zoning of your IT, BGS, and R&D lines without bureaucratic delays.

2. Guided by an Elite Advisory Taskforce

While ConglomerateIT provides the nimble, high-touch corporate vehicle, your centre is deployed by our handpicked Advisory Taskforce. We have assembled a specialized ecosystem of industry veterans who possess a combined 40+ years of enterprise scaling experience. From our Real Estate Lead who has delivered massive commercial fit-outs in India's top tech hubs, to our international legal compliance counsel, your centre is backed by proven enterprise-grade capability.

- De-Risked Model

We believe trust is earned through execution, not assumed. Under our BOT Model, your organization takes on zero initial real estate or infrastructure liability. We launch your first core cohorts right inside our pre-configured premises. This serves as a low-risk Proof-of-Concept Phase, giving your executive board a transparent environment to evaluate our recruitment speed, audit our operational rigor, and test our data isolation protocols before a single brick is laid for a standalone site.

- Absolute Open-Book Governance

To eliminate the fear of hidden vendor premiums, ConglomerateIT operates with absolute transparency. We deploy a Shared Financial Dashboard that grants your leadership real-time, line-item visibility into every verified expense—from individual engineer salaries to localized seat utility bills. Because our incentives are perfectly aligned through a flat, predictable management markup, we function purely as your transparent local arm. What we see, you see.

## How It Works for ConglomerateIT and BOSE

To ensure absolute cultural alignment, technical quality, and seamless operational flow, BOSE organization will deploy a core group of Bridge Leaders (ideally 5+ senior executives) directly into the centre.

These leaders act as the critical strategic conduit, connecting your global headquarters directly to the engineering and operational workforce sitting inside ConglomerateIT's secure facility.

To guarantee flawless operational execution and absolute strategic clarity, ConglomerateIT operates under a strict, pre-defined RACI matrix. This framework ensures that while your Bridge Leaders retain absolute Accountability (A) and Authority over strategic direction, engineering code, and talent culture, ConglomerateIT accepts full Responsibility (R) for absorbing all local operational friction, payroll compliance, network air-gapping, and facility management.

By establishing these razor-sharp operational boundaries from day one, we eliminate governance overlaps and ensure a completely seamless, zero-shock transition whenever the final transfer milestone is triggered."

## GCC Governance: RACI Matrix

(Responsible: Executes the work | Accountable: Final decision maker/sign-off | Consulted: Provides input | Informed: Kept updated)

| Functional Pillar | Client HQ | Client Bridge Leaders | ConglomerateIT Platform |
| --- | --- | --- | --- |
| Strategic Direction & Budgeting | A | R | C |
| Engineering Delivery & Code Quality | I | A / R | I |
| IT Division Setup (CI/CD Pipelines) | I | A | R (Deployment) |
| BGS Compliance (SOC 2, GDPR Data Privacy) | I | A (Audit) | R (Implementation) |
| R&D Air-Gapped Network & Physical Security | I | A (Audit) | R (Execution) |
| Talent Acquisition (Candidate Sourcing) | I | C | A / R |
| Final Hiring Approval & Cultural Fit | I | A / R | I |
| Local Payroll, Benefits & Tax Filing | I | I | A / R |
| Real Estate Sourcing & Facility Build | I | C | A / R |
| Transition & Migration Execution | I | A |  |

## ConglomerateIT GCC Performance-Linked KPI Matrix

| Functional Pillar | Key Performance Indicator (KPI ) | Target SLA / Benchmark |
| --- | --- | --- |
| 1. Setup & Infrastructure | Workspace Readiness & Network Provisioning for the air-gapped zones. | 100% operational setup within 30 days of signed contract (IT/BGS/R&D firewalls live). |
| 2. Talent Acquisition | Time-to-Hire for core divisions from final job profile validation. | • IT & BGS Track: 45 days. • R&D Track: 60 days. |
| 3. Workforce Continuity | Infant Attrition Rate tracking headcount stability during an employee's first 180 days. | 10% annualized attrition across all divisions during the incubation phase. |
| 4. Technical Security | Network Circuit Uptime & firewall availability for client-dedicated ISP loops. | 99.95% Network Uptime (excluding pre-approved weekend maintenance windows). |
| 5. Financial Governance | Open-Book Ledger Accuracy mapping payroll actuals and utility pro-rates. | 100% itemized billing transparency with zero accounting variance during audits. |

## How These KPIs Are Monitored Daily

To avoid any administrative burden on your team, ConglomerateIT establishes a three-tiered governance cadence led by your on-site Bridge Leaders:

- Daily Telemetry Dashboard: Your Compliance and Security Head gets real-time digital readouts of network firewall logs, biometric access logs, and internet circuit uptimes.

- Monthly Open-Book Reconciliation: Your Finance Head gains complete visibility to cross-check all payroll records, landlord receipts, and third-party bills against the active ledger before invoice approval.

- Quarterly Steering Committee Review: ConglomerateIT’s founders meet directly with your Site Lead to audit overall talent velocity, evaluate retention benchmarks, and formally sign off on milestone-linked fee adjustments.

## Three-Tier GCC Governance Architecture

| Governance Tier | Frequency & Audience | Core Focus Area |
| --- | --- | --- |
| Tier 1: Daily Telemetry | Daily Cadence • Client Compliance Head • Client Chief Architect • ConglomerateIT IT Team | Real-Time Infrastructure & Data Security |
| Tier 2: Monthly Reconciliation | Monthly Cadence • Client Finance Controller • ConglomerateIT Accounts Lead | Open-Book Financial & Payroll Validation |
| Tier 3: Quarterly Steering | Quarterly Cadence • Client Site Head / Country Lead • ConglomerateIT Founders | Executive Performance & Strategy Audit |

| Pricing Baseline | Rigid hourly/monthly rates per head | Variable direct entity overhead | Audited actual local expenses |
| --- | --- | --- | --- |
| Vendor Markup / Margins | Opaque 25% to 40% blended into rates | Zero external markup | Transparent, ~15% management fee |
| Long-Term TCO (Year 3+) | Highest (costs compound as team scales) | Efficient at massive scale (>500 heads) | Lowest overall Total Cost of Ownership |

## ConglomerateIT GCC Performance-Linked KPI Matrix

| Financial Metric | Traditional Outsourcing | Pure DIY GCC (In-House) | ConglomerateIT’s Hosted BOT / GCC-as-a-Service |
| --- | --- | --- | --- |

## Ownership and Responsibility Matrix

| Category | Task / Responsibility | ConglomerateIT | GCC Customer (Global Client) |
| --- | --- | --- | --- |
| Legal | Entity Ownership | Provides the Legal Entity | Uses the "Virtual" Entity |
|  | Employment Contract | Legal Employer (Signer) | Strategic Co-signatory |
|  | IP Ownership | Protects (via contracts) | Legal Owner of all IP |
| People | Talent Sourcing | Finds & Screens talent | Final Selection & Interview |
|  | Performance Review | HR Administration | Primary Reviewer |
|  | Promotions/Hikes | Processing & Execution | Decision Maker |
|  | Discipline/Exits | Local Legal Handling | Initiates Request to Terminate |
| Finance | Salary Payments | Execution (Disburses) | Funding (Provides capital) / Reimburses |
|  | Taxes & PF | Files & Deposits with Govt | Reimburses as a Cost |
|  | Office Rent & Ops | Manages Vendor Payments | Reimburses & Pays Monthly Service Fee |
| Daily Ops | Work Management | Local Supervision | Direct Task Assignment |
|  | Working Hours | Local Compliance | Sets Global Time zone |
|  | IT Infrastructure | Procures & maintains | Defines Technical Standards |
|  | Culture | Local Morale/Events | Brand Identity & Values |
| Risk | Labour Law Risk | Manages Compliance | Indemnifies ConglomerateIT |
|  | Data Security | Physical/Network Security | Encryption/Software Policy |

When it’s decided to transition from GCC-as-a-Service (hosted by ConglomerateIT) to a Wholly Owned Subsidiary (owned by the Customer), ConglomerateIT enter the "Transfer" phase of the Build-Operate-Transfer (BOT) model.

At this stage, the responsibility shifts from Operations to Asset & Talent Migration.

| Category | Task / Responsibility | ConglomerateIT | GCC Customer (Global Client) |
| --- | --- | --- | --- |
| Legal | Entity Formation | Provides local advisory | Primary Owner (Incorporate New Co) |
|  | Contract Novation | Prepares "Transfer of Service" docs | Signs new employment offers |
|  | License Transfer | Relinquishes local licenses | Applies for new PAN/TAN/GST |
| Talent | Continuity of Service | Calculates Gratuity/Leaves | Primary Owner (Recognizes past tenure) |
|  | Employee Consent | Manages 1-on-1 "Change" comms | Welcomes team to the global brand |
|  | Retention Bonus | Administers final payment | Funding Owner (Pays for loyalty) |
| Assets | IT Hardware | Sells/Transfers assets at Book Value | Buyer (Purchases laptops/servers) |
|  | Office Lease | Facilitates "Novation" of Lease | Signs new Lease Agreement |
| Finance | Statutory Closure | Closes PF/ESI records for project | Opens new PF/ESI accounts |
|  | Final Audit | Provides clear "No Dues" cert | Primary Owner (Due Diligence) |
|  | Transfer Fee | Invoices agreed "Success Fee" | Pays Transfer/Buyout Fee |

## For "heavy" physical items like laptops, servers, and furniture, ConglomerateIT will request a funded-in-advance model with the BOSE on mutual agreements, where the BOSE pays for major assets before you purchase them.

| 4.8 | Talent Strategy and Organisation Design |
| --- | --- |

## ConglomerateIT's Talent Intelligence Advantage

ConglomerateIT's GCC experts maintain quarterly-updated salary benchmarks, attrition data, and time-to-fill intelligence for 120+ IT and GBS role families across all four shortlisted cities. Our talent data is sourced from live hiring activity across several GCC BOSEs: not survey-based estimates. The benchmarks below reflect Q1 2026 data.

## IT Role Salary Benchmarks: Annual CTC in USD (Q1 2026)

| Role | Bengaluru | Hyderabad | Pune | Chennai |
| --- | --- | --- | --- | --- |
| Salesforce Developer (Mid, 3–6 yrs) | $28,000–$38,000 | $24,000–$33,000 | $25,000–$34,000 | $23,000–$32,000 |
| SAP ABAP / Basis (Mid) | $30,000–$42,000 | $26,000–$36,000 | $27,000–$37,000 | $25,000–$35,000 |
| SAP S/4HANA Functional (Senior) | $50,000–$70,000 | $43,000–$61,000 | $45,000–$63,000 | $42,000–$59,000 |
| MuleSoft Developer (Mid) | $32,000–$44,000 | $28,000–$39,000 | $29,000–$40,000 | $27,000–$37,000 |
| QA Automation Engineer (Mid) | $22,000–$32,000 | $19,000–$28,000 | $20,000–$29,000 | $18,000–$27,000 |
| DevOps / SRE Engineer (Mid) | $28,000–$40,000 | $24,000–$35,000 | $25,000–$36,000 | $23,000–$33,000 |
| Cloud Architect (Senior, AWS/Azure/GCP) | $50,000–$70,000 | $43,000–$61,000 | $45,000–$63,000 | $42,000–$59,000 |
| Cybersecurity Engineer (Mid) | $35,000–$50,000 | $30,000–$44,000 | $31,000–$45,000 | $29,000–$42,000 |
| IT Delivery Manager | $55,000–$75,000 | $47,000–$65,000 | $49,000–$67,000 | $45,000–$63,000 |

Note: All benchmarks are CTC (Cost to Company), inclusive of base, performance bonus (10–20%), employer PF contribution (12% of basic), and standard India allowances. Contractor/agency rate benchmarks maintained separately. Niche-skill premiums (SAP BTP, MuleSoft architect, senior SecOps) add 15–25% to band midpoints.

## GBS Role Salary Benchmarks: Annual CTC in USD (Q1 2026)

| Role | Bengaluru | Hyderabad | Pune | Chennai |
| --- | --- | --- | --- | --- |
| Order Management Analyst (Mid) | $12,000–$18,000 | $10,000–$16,000 | $11,000–$17,000 | $10,000–$15,500 |
| Customer MDM Specialist (Mid) | $13,000–$19,000 | $11,000–$17,000 | $12,000–$18,000 | $11,000–$16,500 |
| Procurement Operations Analyst | $12,000–$18,000 | $10,000–$16,000 | $11,000–$17,000 | $10,000–$15,500 |
| Product MDM / PIM Analyst | $13,000–$18,000 | $11,000–$16,000 | $12,000–$17,000 | $11,000–$15,500 |
| PMO Analyst / Project Coordinator | $15,000–$22,000 | $13,000–$19,000 | $14,000–$20,000 | $13,000–$18,500 |
| GBS Process Lead / Manager | $25,000–$38,000 | $21,000–$33,000 | $22,000–$34,000 | $20,000–$31,000 |
| GBS Operations Director | $55,000–$75,000 | $47,000–$65,000 | $49,000–$67,000 | $45,000–$62,000 |
| India Site Leader (GCC Head) | $90,000–$130,000 | $78,000–$115,000 | $80,000–$118,000 | $75,000–$110,000 |

## Hiring Metrics by Role Family

| Role Family | Time to Fill | Year 1 Attrition | Agency Support Needed? |
| --- | --- | --- | --- |
| Salesforce (all levels) | 35–55 days | 12–15% | For senior / specialist roles |
| SAP (core roles) | 40–65 days | 13–16% | For S/4HANA, BTP specialists |
| MuleSoft | 50–75 days | 14–18% | Yes, scarce across all cities |
| QA / Automation | 25–40 days | 10–13% | No |
| DevOps / Cloud | 30–50 days | 11–14% | Occasionally for senior |
| Cybersecurity | 45–70 days | 12–16% | For senior SecOps roles |
| GBS Operations (all) | 20–35 days | 8–12% | No |
| PMO / Transformation | 30–45 days | 9–12% | No |
| Site Leader and senior leadership | 60–90 days | 6–10% | Yes, executive search recommended |

## R&D Talent – the Special Talent

All figures below are approximate mid-market ranges based on ConglomerateIT's current placement data (2025-2026). Premium/scarce roles may be 20-30% above these bands.

| Role | City | Salary Band (INR L/yr) | USD Equiv. | Time to Fill | Difficulty | Attrition Risk |
| --- | --- | --- | --- | --- | --- | --- |
| Audio DSP Engr | Bengaluru | 45–75L | $54–90K | 10–14 wks | High | Moderate |
| Audio DSP Engr | Hyderabad | 38–65L | $45–78K | 12–16 wks | High | Moderate |
| BT Firmware Engr | Bengaluru | 30–55L | $36–66K | 8–12 wks | Moderate-High | Moderate |
| BT Firmware Engr | Pune | 28–50L | $34–60K | 10–14 wks | Moderate | Low-Mod |
| Mobile App (iOS/Android) | Hyderabad | 22–45L | $26–54K | 6–10 wks | Moderate | Moderate |
| Mobile App (iOS/Android) | Bengaluru | 25–50L | $30–60K | 6–8 wks | Moderate | Moderate-High |
| RTOS/Embedded Linux | Bengaluru | 28–52L | $34–62K | 8–12 wks | Moderate | Moderate |
| RTOS/Embedded Linux | Hyderabad | 25–48L | $30–58K | 8–12 wks | Moderate | Low-Mod |
| TinyML / Edge AI | Bengaluru | 35–65L | $42–78K | 14–20 wks | Very High | High |
| Wearable Systems Engr | Bengaluru | 30–58L | $36–70K | 12–18 wks | High | Moderate |

## Talent Acquisition and Retention Strategy

- Employer brand: Designed before the first job posting goes live. ConglomerateIT's Employer Branding practice builds BOSE's India EVP covering career growth narrative, compensation positioning, culture, and learning investment. This is the single most effective attrition-prevention tool available.

- Sourcing: Direct sourcing via LinkedIn, Naukri, Instahyre for IT; functional GBS job boards and referral programs for GBS roles; ConglomerateIT talent network (250,000+ professionals across active GCC BOSE.

- Assessment: Structured competency-based interviews, technical assessments (role-specific, calibrated to BOSE's global standards), and culture-fit evaluation.

- Retention: India-aligned compensation bands, performance-linked variable pay (10–20% of CTC), structured L&D, clear career-path design, and manager effectiveness programs from Month 1.

| 4.9 | Facilities, Technology, Security, and Business Continuity |
| --- | --- |

For the Managed & Hosted GCC, ConglomerateIT provides a secure, enterprise-grade environment that insulates the Client from real estate complexities while maintaining rigorous data and intellectual property boundaries.

Facilities Strategy & Workplace Setup

To achieve an optimal balance between rapid deployment and long-term scaling, ConglomerateIT utilizes a phased, plug-and-play real estate strategy.

- Temporary/Incubation Workspace: Upon contract signature, ConglomerateIT will immediately provision a secure, move-in-ready team space within our existing enterprise technology centre. This ensures the first wave of engineers can onboard, complete knowledge transfer, and begin development within 14 calendar days without waiting for custom real estate builds.

- Dedicated Office Selection: Concurrently, ConglomerateIT will allocate a dedicated zone within our premier technology facility to serve as the GCC. If the Client requests a net-new location, ConglomerateIT will manage the commercial site selection, prioritizing Tier-1 tech parks featuring standard amenities such as dual-grid power feeds, multi-carrier fibber entrances, and high-ratio parking.

- BOSE Branding: ConglomerateIT will create a physical "Oasis"—a completely segregated office perimeter enclosed by floor-to-ceiling walls. This area will be customized with Client branding, specialized meeting rooms, and acoustic treatment.

Baseline Technology & Infrastructure Configuration

- Network Architecture: The dedicated zone is built on an isolated network tier. ConglomerateIT provisions dual, geographically redundant 1Gbps Dedicated Internet Leased Lines (DILL) operating in an active-active configuration with automated failover. Internal Wi-Fi and LAN infrastructure utilize dedicated corporate subnets shielded by enterprise-grade Next-Generation Firewalls (NGFW).

- Endpoint Specifications: Developers are issued high-performance enterprise laptops (Minimum Specification: Core i7/Ryzen 7 processor, 32GB RAM, 1TB NVMe SSD). All endpoints undergo hardware hardening, baseline patching, and are packaged with a unified endpoint management agent before handover.

- Identity & Access Control: Physical entry requires dual-factor authentication (Biometric fingerprint scanning paired with encrypted HID corporate access badges). Digital entry utilizes zero-trust architecture; remote network access is strictly gated through a Secure Access Service Edge (SASE) client integrated into the Client’s Identity Provider (IdP) for single sign-on (SSO).

- Collaboration Environment: Meeting spaces are equipped with native videoconferencing hardware (e.g., Polycom or Cisco Webex bars), dual display screens, and automated whiteboarding setups optimized for hybrid sprint planning and daily standups across time zones.

Security, Privacy, IP Protection, and BCP

Protecting the Client's digital assets and maintaining operational continuity are core to ConglomerateIT's operational model.

Security & Privacy Safeguards

- Data Loss Prevention (DLP): Endpoints are locked down via strict system policies: local USB storage ports are blocked, clipboard cross-copying out of corporate profiles is restricted, and print-screen capabilities are disabled.

- Regulatory Compliance: The hosted environment is managed to meet stringent SOC 2 Type II and ISO/IEC 27001 data privacy standards. All data processing activities align with international standards such as GDPR and CCPA.

Intellectual Property (IP) Protection

- Cleanroom Environment: No external personal storage devices, cameras, or recording equipment are permitted past the biometric security threshold of the dedicated GCC zone.

- Source Code Governance: No source code is hosted locally within the ConglomerateIT facility. All engineering work occurs within the Client's secure cloud environments (e.g., AWS, Azure, GitHub Enterprise). Local endpoints act strictly as secure access terminals.

Business Continuity Plan (BCP)

- Power & Utility Resilience: The facility features continuous power backup infrastructure, including a centralized Uninterruptible Power Supply (UPS) for instant bridge-power and heavy-duty, dual diesel generators backed by 72-hour on-site fuel reserves.

- Disaster Recovery Protocol: In the event of a severe regional disruption, ConglomerateIT maintains an automated shift-to-remote framework. Employee endpoints are pre-configured with secure cloud-based Virtual Desktop Infrastructure (VDI), allowing the engineering team to transition to remote operations within 2 hours without compromising data compliance.

"At ConglomerateIT, we provide more than just office space; we deliver a resilient, excelling operational ecosystem designed to scale with your ambition. Our strategy eliminates the 'infrastructure headache' by providing physically segregated, branded facilities backed by technology and power. We secure your most valuable asset—your Intellectual Property—through a Defence-in-Depth security framework that combines military-grade network encryption with rigorous physical access controls.

With our integrated Business Continuity Plan, your global operations remain uninterrupted by local disruptions, ensuring your team stays productive regardless of the environment. By partnering with ConglomerateIT, you gain the security of a corporate headquarters with the agility of a startup, all under a transparent, cost-plus model."

| 4.10 | Agency / Partner Strategy and Hybrid Workforce Model |
| --- | --- |

ConglomerateIT applies an asset-backed, data-driven approach to optimize your external vendor landscape, transition critical skill sets, and scale your Managed & Hosted GCC efficiently.

## Vendor Disposition Framework (Sourcing Rationalization)

To evaluate which workloads should be insourced, retained, rebid, or exited, ConglomerateIT applies a Two-Axis Evaluation Matrix assessing Strategic Value to Enterprise against Operational Delivery Performance.

- Insource (Move to GCC): High-performing workloads containing core intellectual property, enterprise data architecture, and strategic product roadmaps.

- Retain with Strategic Partners: High-performing vendors managing niche legacy applications or highly specialized domain-specific workflows that are cost-prohibitive to hire internally.

- Competitively Rebid: Commodity workloads (e.g., manual testing, level-1 support) managed by low-to-mid performing vendors, consolidated to drive volume discounts.

- Exit / Eliminate: Fragmented, low-volume, or poorly performing vendors managing redundant tools or legacy tech stacks slated for deprecation.

## Rate Benchmarking & Savings Strategy

ConglomerateIT removes the guesswork from vendor pricing by utilizing real-time market data to uncover negotiation leverage.

- Rate Benchmarking Approach: We cross-reference your current vendor rate cards against our proprietary Indian tech-talent pricing database. This tracks real-time compensation metrics across Tier-1 tech hubs (Bengaluru, Hyderabad, Pune, NCR).

- Negotiation Levers Identified:

  - Volume Consolidation: Aggregating fragmented workloads from multiple small vendors into a single pool to unlock tiered rate discounts.

  - Pyramid Optimization: Rebalancing top-heavy vendor teams by replacing overpriced mid-level resources with highly productive, cost-effective junior engineers.

- Savings Translation: Transitioning from legacy vendor models to ConglomerateIT's Hosted Cost-Plus ~15% model typically yields net operational savings of 28% to 35%, by directly eliminating high agency gross margins.

## Talent Segmentation (Core Market vs. Premium Skills)

- Core-Market Roles: High-supply profiles (e.g., Full-Stack Java, manual QA, standard DevOps). ConglomerateIT applies strict local compensation caps to eliminate vendor rate inflation. Outliers here indicate hidden vendor markup.

- Premium / Scarce-Skill Roles: Low-supply, high-demand profiles (e.g., GenAI/LLM engineers, specialized cloud architects, cybersecurity data scientists). ConglomerateIT utilizes custom compensation bands and performance-linked retention bonuses for these roles, justifying the talent premium to protect the Client's delivery timeline.

## Multi-City Cross-Border Transition Strategy

ConglomerateIT ensures continuous operations by managing remote transitions across distributed geographies while scaling your central hub.

- Knowledge Transfer Over Distance: If existing vendor work sits in a different city (e.g., Chennai or Mumbai) than your chosen GCC hub, ConglomerateIT deploys an automated virtual Knowledge Transfer (KT) protocol.

- Shadowing & Cutover: The new GCC team in the permanent city remotely shadows the legacy vendor teams via recorded sessions, code walkthroughs, and pair-programming.

- Phased Roll-Offs: Workloads are shifted incrementally—module by module—rather than all at once. Legacy vendor contracts are systematically reduced in steps corresponding to successful GCC milestones, eliminating delivery risk.

## Vendor Consolidation & Rationalization Roadmap

ConglomerateIT’s execution strategy shrinks a fragmented vendor base down to a lean group of strategic partners, reducing management overhead.

- Phase 1: Discover & Audit: Consolidate all external statement of work (SOW) documents, rate sheets, and headcount data into a single master dashboard.

- Phase 2: Tier Categorization: Group vendors into Tier-1 (Strategic Partner), Tier-2 (Niche/Commodity Vendor to be Rebid), and Tier-3 (To be Exited).

- Phase 3: Migration to Hosted GCC: Migrate targeted vendor seats into the ConglomerateIT Hosted GCC, systematically winding down legacy SOWs to achieve an organized, lower-cost vendor footprint.

## Strategic RFP / RFI Requirements for Follow-On Selection

If the Client issues a follow-on RFP for secondary implementation vendors, ConglomerateIT recommends enforcing these specific data-backed criteria:

- Talent Attrition Proof: Request audited annual voluntary attrition rates specifically for the target city over the past 24 months.

- Open-Book Commercial Auditability: Require vendors to explicitly split their billing structures into direct salary costs, facility hosting costs, and gross margins.

- IP & Legal Protection Track Record: Request verified case studies demonstrating legal and logical code isolation practices for Fortune 500 clients.

- BOT Transition Framework Maturity: Force vendors to provide exact contract terms, talent transfer premiums, and asset depreciation timelines governing the eventual transfer option.

| 4.11 | Transition and Launch Planning |
| --- | --- |

## ConglomerateIT Transition Methodology

- Assessment: Document current-state service delivery for each in-scope process. Volume, SLA, pain points, knowledge holders, and system dependencies mapped jointly with incumbents and BOSE stakeholders.

- Wave planning: Prioritize transitions by complexity, risk, volume, and readiness. Wave 1: standardized, high-volume GBS (Order Management, Customer MDM); Wave 2: IT operational roles (DevOps support, QA); Wave 3: complex/niche roles (SAP functional, MuleSoft, Cybersecurity) & R&D.

- Knowledge transfer (per wave): Structured KT protocol, process documentation, shadowing period (2–4 weeks), reverse-shadowing (India team leads, incumbent observes), and explicit sign-off before go-live.

- Hypercare: Daily SLA monitoring, rapid issue resolution, structured lessons-learned cycle, and stabilization sign-off before full handover.

## Day 1 Launch Readiness Gates

| Domain | Gate Criteria |
| --- | --- |
| Legal & Compliance | Entity active, all registrations complete, employment contracts signed |
| Facilities | Temporary office open, IT infrastructure live and tested |
| HR & Payroll | Payroll system live, policies published, HRIS active, bank accounts open |
| IT & Security | VPN live, endpoints configured, SOC extended to India, DPDP compliant |
| Leadership Hiring | Site Lead, HR, IT, Finance, GBS heads in seat and onboarded |
| Cohort 1 Hiring | First 50 FTE offers accepted, background checks complete, onboarding scheduled |
| Governance | Steering charter signed, PMO operating, RAID log live |
| KT Sign-Off (Wave 1) | Wave 1 KT complete, shadow period done, SLA baseline established |
| Day 1 Go-Live | All gates green, hyper care team activated, escalation paths tested |

## Incumbent Vendor Transition

- Contract review: ConglomerateIT reviews all current vendor contracts for notice period requirements, IP ownership, KT obligations, and exit penalty exposure within the first 4 weeks.

- Notice management: Formal notice to incumbents initiated only after India model readiness is confirmed, avoiding service gaps.

- KT from incumbents: Structured protocol requiring vendors to document all runbooks, escalation contacts, and process knowledge before exit sign-off.

- Parallel run: For critical IT operations roles, a 4–6 parallel-run period before the incumbent exits, ensuring zero service disruption to BOSE's business.

| 4.12 | Tools, Methods, and Use of AI |
| --- | --- |

## ConglomerateIT Lean-GCC as the GCC Accelerator Platform (GAP)

As ConglomerateIT enters its next phase of global expansion, establishing a presence in premier technology hubs like India is critical to maintaining our competitive edge. Historically, setting up a Global Capability Centre (GCC) required a massive upfront capital commitment, long legal timelines, and thousands of linear headcounts.

ConglomerateIT is bypassing this legacy model entirely. By leveraging a modern, Agentic-First Architecture, we are establishing a "Lean GCC" in India. This model deploys autonomous AI multi-agent networks as our foundational execution layer across all infrastructure, talent acquisition, and operational workflows. Rather than scaling through human-heavy operations, ConglomerateIT will utilize a lean ecosystem where highly skilled local engineers serve as "Agent Supervisors"—achieving the operational output, speed, and market velocity of an enterprise ten times our size.

| 4.13 | Risks, Dependencies, and Assumptions |
| --- | --- |

## Top Risks and Mitigations

| Risk | Impact | Likelihood | ConglomerateIT Mitigation |
| --- | --- | --- | --- |
| Permanent establishment exposure from US contracting structure | High | Medium | Intercompany agreement and PE review by Day 30; all employment flows through India entity |
| Delayed entity activation (missing registrations, banking delays) | High | Low-Med | Entity audit in Week 1; parallel-track all registrations; ConglomerateIT bank relationships accelerate account opening |
| Inability to fill niche IT roles in timeline (MuleSoft, SAP BTP, CyberSec) | Medium | Medium | BOT arrangement pre-agreed; ConglomerateIT talent network pre-seeding; executive search for lead roles |
| City down-select delayed beyond Month 2 | High | Low | City assessment delivered Week 3; decision criteria and timeline agreed in Week 1 kick-off |
| Attrition of Day 1 leadership hires during ramp | High | Low | Retention-by-design from offer stage; signing bonus for critical leadership roles; career-path visibility |
| Incumbent vendor resistance to knowledge transfer | Medium | Medium | Contractual KT obligations enforced; ConglomerateIT KT protocol; parallel-run period for critical roles |
| Rate-lock assumptions with incumbents not achievable | Medium | Medium | Early contract review; termination-for-convenience clauses identified; competitive RFP as leverage |
| Over-reliance on a single ConglomerateIT resource | Medium | Low | ConglomerateIT proposes multi-workstream team; no single point of failure; named backups for all key roles |

## Key Assumptions

- Executive sponsor availability of 2–4 hours per week during setup phase for key decisions (city down-select, model confirmation, leadership hire approvals).

- Role demand clarity, specific JDs and headcount targets per function, confirmed by end of Month 1.

- BOSE Finance, Tax, and Legal teams available for intercompany agreement review and transfer pricing sign-off within 30 days of engagement start.

- Incumbent vendor contracts have enforceable KT obligations or standard notice provisions that allow parallel-run planning.

| 5 | Required Deliverables and Output Standards |
| --- | --- |

ConglomerateIT confirms its commitment to provide all 13 required deliverables listed in RFI Section 6. The table below maps each client requirement to the specific section of this response where the content is addressed, confirms what each deliverable contains, states the proposed delivery timing, and explains how BOSE can reuse or transition each output independently of ConglomerateIT if required.

| Workstream | Required Deliverable | Minimum Expected Content / Questions Supplier Must Answer | ConglomerateIT Response, Confirmation, Content, Timing, and Reusability |
| --- | --- | --- | --- |
| Strategy & Business Case | Delivery model strategy recommendation and business case | Recommended model, target scope, cost drivers, benefits, risks, assumptions, and phased roadmap | YES, Section 1 (Executive Summary) and Section 2 (Understanding of BOSE's Challenge) present ConglomerateIT's Hosted BOT / GCC-as-a-Service recommendation with full cost-benefit rationale, risk profile, and phased roadmap across Foundation, Scaled Delivery, Capability Leadership, and Innovation Ownership stages. Deliverable: Business case deck (Excel + PPT), delivered. Reusability: Fully editable; structured to serve directly as input to an RFP or implementation planning phase. No recreation required. Acceptance criterion: Executive sponsor sign-off on preferred model and phased roadmap. |
| Setup Planning | Launch roadmap and workplan | Detailed phase plan, milestones, dependencies, critical path, BOSE participation required, and launch-readiness gates | YES, The 'Workplan, Timeline, and BOSE Participation Required' section provides a four-phase DIG (Design–Implement–Govern) workplan with a parallel GR&D track, covering milestones, deliverables, and BOSE inputs for each phase. Launch-readiness gates are defined in Section 10.2 (Day 1 Launch Readiness Gates) across Legal, Facilities, HR, IT, Leadership Hiring, Cohort 1, Governance, and KT Sign-Off. Deliverable: Phase plan (PPT + Excel Gantt), delivered. Reusability: Fully editable milestone tracker; transferable to any successor partner or BOSE PMO without rework. Acceptance criterion: All Phase 1 gate criteria agreed with executive sponsor and BOSE PMO lead. |
| Operating Model | Target operating model design | Org structure, governance, decision rights, service ownership, KPI framework, escalation model, and interaction with global BOSE teams | YES, Section 4 (Operating Model and Governance) delivers the complete target operating model: org structure and decision rights under the cost-plus BOT framework; RACI matrix (Section 4.6) covering all functional pillars; KPI framework with malus penalties (Section 4.7); three-tier governance architecture (Daily Telemetry, Monthly Reconciliation, Quarterly Steering, Section 4.9); and full interaction model between India operations and BOSE global teams via Bridge Leaders (Section 4.5). Deliverable: Operating model design (PPT + org chart), delivered. Reusability: Editable Visio/PPT org chart; governance charter transferable to BOSE PMO or new partner. Acceptance criterion: BOSE Site Lead and executive sponsor approve governance structure and RACI before Phase 3 activation. |
| Legal / Tax / Compliance | Existing India entity readiness and operationalization checklist | Registrations, statutory requirements, labor-law considerations, tax/finance setup items, policies, and ownership matrix | YES, Section 4 (Legal, Tax, and Compliance Readiness) covers contracting structures (US entity vs India entity, Sections 4.1–4.3), transfer pricing Safe Harbour alignment, GST implications, and entity operationalization approach (Section 4.4). ConglomerateIT coordinates with a Big 4 tax partner for statutory registrations, PAN/TAN/GST activation, EPF/ESI setup, labour law obligations, and permanent establishment risk management. Deliverable: Entity readiness checklist + activation plan (PPT + checklist), delivered. Appendix D confirms all workstream inclusions. Reusability: Ownership matrix clearly identifies what ConglomerateIT owns, what is coordinated with specialists, and what BOSE must own. Fully transferable to BOSE's own legal/tax team or a successor advisor. Acceptance criterion: BOSE Finance, Tax, and Legal sign-off on entity activation sequence and TP structure within 30 days of engagement start. |
| Talent | Talent strategy and hiring plan | Role architecture, hiring sequence, leadership roles, salary bands, recruiting channels, employer branding, onboarding, and retention actions | YES, Section 8 (Talent Strategy and Organisation Design) provides the complete talent plan: IT salary benchmarks by city (Section 8.2), GBS salary benchmarks (Section 8.3), hiring metrics by role family including time-to-fill, Year 1 attrition, and agency need (Section 8.4), and sourcing and retention strategy (Section 8.5). The 'Team Structure and Key Roles' section covers the Day 1 leadership spine. GR&D engineering salary bands are provided in Part II, Section 1.3. FTE benchmarks are explicitly separated from agency/contractor rate benchmarks. Niche-skill premiums (SAP BTP, MuleSoft Architect, Senior SecOps, TinyML) are identified with 15–30% uplift guidance. Deliverable: Talent & hiring plan (Excel + PPT), delivered. Reusability: Role architecture and salary benchmark data are structured for direct import into BOSE's HRIS and ATS. Transferable to an internal TA team or new search partner. Acceptance criterion: BOSE HR approves JDs, compensation bands, and Day 1 leadership hiring sequence before Phase 3 recruitment activation. |
| Facilities & Technology | Site and infrastructure setup plan | Workspace strategy, technology stack, security controls, business continuity requirements, and launch dependencies | YES, Section 9 (Facilities, Technology, Security, and Business Continuity) covers the full site and infrastructure plan: phased workspace strategy (temporary incubation → dedicated facility), network architecture (dual 1Gbps DILL, NGFW, zero-trust SASE), endpoint specifications and hardening, biometric and HID access controls, DLP controls, SOC 2 Type II / ISO 27001 compliance, IP protection (cleanroom environment, source code governance), and BCP (72-hour fuel reserves, 2-hour remote VDI failover). Deliverable: Site and infrastructure setup plan (PPT + configuration checklist), delivered as part of Phase 3 setup planning (Week 10). Reusability: Technology stack and security control specifications are documented in BOSE-owned format; fully portable to BOSE IT and Security teams or a successor managed services provider. Acceptance criterion: BOSE IT and CISO sign-off on security architecture before endpoint deployment and VPN activation. |
| Transition | Transition and stabilization plan | Candidate functions for migration, wave plan, knowledge-transfer approach, transition risks, hyper care/stabilization model, and success metrics | YES, Section 10 (Transition and Launch Planning) covers ConglomerateIT's full transition methodology under the DIG framework: wave planning by complexity, risk, volume, and readiness (Wave 1: standardised GBS; Wave 2: IT operational; Wave 3: complex/niche, Section 10.1); structured KT protocol with shadow and reverse-shadow periods; Day 1 launch readiness gates (Section 10.2); incumbent vendor transition including parallel-run period and contractual KT obligations (Section 10.3); and hyper care model. Insource/outsource recommendation is provided by role family; wave plan identifies dependencies and continuity risks at each transition stage. Deliverable: Transition and stabilisation plan (PPT + Excel wave tracker), delivered Week 8. Reusability: Wave plan and KT tracker are fully editable and structured for hand-off to BOSE's own transition team or a successor delivery partner. Acceptance criterion: Wave 1 KT sign-off completed and SLA baseline established before Day 1 go-live. |
| Program Management | Governance and reporting pack | Steering structure, PMO cadence, RAID log approach, status reporting, decision log, and communications plan | YES, Section 4.9 (Three-Tier Governance Architecture) defines the full governance model: Daily Telemetry (infrastructure and security, automated Fortinet/Cisco dashboard); Monthly Reconciliation (open-book financial and payroll validation); Quarterly Steering (executive performance and strategy audit). The PMO is active from Week 1. RAID log, status reporting, and decision log cadence are defined in Section 4.8. The 'Team Structure' section confirms a dedicated PMO/Program Manager role throughout the engagement. Deliverable: Governance and reporting pack (PPT + templates), delivered Week 6. Reusability: All governance templates, RAID logs, and steering decks are BOSE-owned, fully editable, and immediately operational without rework. Structured for transition to BOSE's own PMO function at any point. Acceptance criterion: Steering committee charter signed by executive sponsor and BOSE Site Lead before end of Week 2. |
| Sample Outputs | Representative templates / examples | Sample dashboards, trackers, governance artifacts, hiring tracker, milestone plan, or deliverable excerpts | YES, Appendix C (Sample Deliverables) catalogues nine sample outputs available from live ConglomerateIT client engagements: GCC Operating Model Design (PPT); City Assessment Scoring Model (Excel); Talent and Compensation Benchmark Report (Excel); Transition Wave Plan and KT Tracker (Excel + PPT); Day 1 Launch Readiness Checklist (Excel); Governance and Steering Pack (PPT + templates); Open-Book Financial Dashboard (Excel); GR&D Engineering Hiring Tracker and Onboarding Checklist (Excel); and R&D GCC Transition Case Study Deck (PPT). All samples are available in editable format upon request under NDA. |
| Location Strategy | Shortlisted-city support assessment | Scoring criteria and weighting, city-by-city role analysis, and expansion triggers | YES, Section 3 (India Location Strategy) provides the complete city assessment: six-attribute scoring framework covering Talent Pool, Infrastructure, Government Policies, Cost of Operations, Quality of Life, and Partner Ecosystem (Section 3.1); GCC Location Suitability Rating Matrix with transparent scores out of 10 for all four shortlisted cities (Section 3.2); city-specific narrative on strengths, constraints, and expansion triggers (Section 3.3); and a dual-hub recommendation (Hyderabad primary; Bengaluru R&D/BCP secondary). For GR&D engineering, Part II Section 2 provides a supplemental city-by-city engineering capability assessment. Deliverable: City Assessment Report (Excel scoring model + PPT), delivered. Reusability: Scoring model is fully transparent and editable. Assumptions are stated; BOSE can adjust weightings. Transferable to BOSE's own real estate or facilities team. Acceptance criterion: City down-select confirmed by executive sponsor. |
| Talent & Workforce | Role architecture and talent plan for IT and GBS | Role families, salary bands, time-to-fill assumptions, leadership spine, insource vs. outsource recommendations, and Day 1/Year 1 hiring plan | YES, Sections 8.2 (IT salary benchmarks by city), 8.3 (GBS salary benchmarks), and 8.4 (hiring metrics by role family) provide city-specific salary bands in USD, time-to-fill ranges, Year 1 attrition rates, and agency support flags across all IT and GBS role families in scope. The 'Team Structure' section identifies the full Day 1 and Year 1 leadership spine (Site Lead, HR, Finance, IT/Security, GBS Operations). FTE salary benchmarks are explicitly separated from agency/contractor rate benchmarks. Niche-skill premiums are identified by role family. Insource vs. outsource recommendations follow the Two-Axis Evaluation Matrix in Section 12.1. Deliverable: Role architecture and talent plan (Excel + PPT), delivered Week 4–5 using GAP platform live hiring data. Reusability: Role architecture and benchmark data structured for direct use in JD development, HRIS configuration, and offer management. Fully transferable to BOSE's internal TA team. Acceptance criterion: BOSE HR and functional leads approve final role list and salary bands before recruiting activation. |
| Agency / Hybrid Model | Partner strategy and transition recommendation | Incumbent assessment, strategic-partner vs. reduce-to-exit logic, BOT/incubate-to-captive options, rate benchmark view, and transition approach | YES, Section 12 (Agency / Partner Strategy and Hybrid Workforce Model) covers the complete partner strategy: vendor disposition framework using a Two-Axis Evaluation Matrix, Insource vs. Retain vs. Rebid vs. Exit (Section 12.1); rate benchmarking methodology and negotiation levers including volume consolidation and pyramid optimisation (Section 12.2); talent segmentation separating core-market from premium/scarce-skill roles (Section 12.3); multi-city cross-border transition with virtual KT protocol and phased roll-off (Section 12.4); vendor consolidation roadmap across Tier 1/2/3 categorisation (Section 12.5); and follow-on RFP/RFI criteria including open-book commercial auditability and BOT transition framework maturity (Section 12.6). Deliverable: Partner strategy and transition recommendation (PPT + Excel), delivered. Reusability: Vendor disposition matrix and rate benchmark data are structured for direct use in BOSE's Procurement-led rebid or RFP process. Acceptance criterion: BOSE Procurement confirms incumbent contract data availability to enable rate benchmarking. |
| Commercial / Contracting | Savings levers, BOT/hybrid support, and contract-model recommendation | Agency rate-negotiation opportunities, local contracting implications, U.S.-to-India contracting trade-offs, and key tax/PE dependencies | YES, Section 4 (Legal, Tax, and Compliance) covers U.S. entity vs. India entity contracting trade-offs in detail (Sections 4.1–4.3), including GST implications, transfer pricing risk, foreign-exchange clearance, FIRC requirements, and PE exposure. Section 15 (Commercial Response) provides the cost-plus pricing framework. Section 15.2 (Commercial Assumptions) identifies the principal savings levers: location cost differential, insourcing from incumbents, rate renegotiation through volume consolidation and pyramid optimization, and the shift from opaque outsourcing margins to a transparent Cost + 15% model. Deliverable: Savings levers and contract-model recommendation memo (PPT + Excel), delivered as part of the commercial response. Reusability: The savings model is editable and can be updated as BOSE refines scope, city mix, or timing assumptions. It can be used directly in procurement, legal, finance, or executive decision-making without dependence on ConglomerateIT. Acceptance criterion: BOSE Finance and Procurement confirm the preferred contracting model and commercial assumptions for Phase 1 mobilization. |

## Deliverable Quality Standards: ConglomerateIT Compliance Confirmation

ConglomerateIT acknowledges and confirms compliance with all nine quality standards specified in RFI Section 6.1. The table below states how each standard is met in this response and in ConglomerateIT's delivery model.

| Deliverable Quality Standard (RFI Section 6.1) | ConglomerateIT Compliance Confirmation |
| --- | --- |
| All deliverables must be fact-based, practical, and immediately actionable. | Confirmed. All ConglomerateIT deliverables are grounded in live hiring data, active GCC engagement experience, and real market intelligence, not survey reports. Every deliverable is designed for immediate use by BOSE without requiring additional analysis or reformatting. |
| Deliverables must be provided in editable formats where applicable. | Confirmed. All deliverables are provided in Microsoft Office editable format (PowerPoint, Excel, Word). No PDF-only outputs unless specifically agreed. Source files and templates are included with every deliverable package. |
| Deliverables must be fully reusable by BOSE without requiring any work to be recreated. | Confirmed. ConglomerateIT structures all outputs as BOSE-owned assets from the moment of delivery. Governance packs, hiring trackers, wave plans, financial dashboards, and scoring models are designed for direct operational use, no post-engagement rework required. Transition to a successor partner or BOSE's internal team requires no recreation. |
| Suppliers must distinguish clearly between current-phase outputs and later-phase recommendations. | Confirmed. Every deliverable in Section 14 (Deliverables Matrix) includes a proposed timing column (Week 3 through Week 10+) that distinguishes current-phase outputs from later-phase recommendations. Phase-specific outputs are labelled accordingly in all deliverable documents. |
| Suppliers should identify acceptance criteria or success measures for major deliverables. | Confirmed. Acceptance criteria for major deliverables are identified in the 'ConglomerateIT Response' column of the Required Deliverables table above. The Section 14 Deliverables Matrix further identifies BOSE inputs required for each deliverable. Formal sign-off gates are defined in Section 10.2 (Day 1 Launch Readiness Gates). |
| Location deliverables: include a transparent scoring model, role-level city commentary, and stated assumptions. | Confirmed. Section 3.2 provides a fully transparent, weighted scoring matrix (10-point scale across 6 attributes) for all four shortlisted cities. Role-level city commentary is provided in Section 8 (IT and GBS salary benchmarks by city) and Part II Section 2 (GR&D engineering city assessment). All scoring assumptions are explicitly stated and the model is editable by BOSE. |
| Talent deliverables: separate BOSE-hired salary benchmarks from agency/contractor rate benchmarks; identify where niche-skill premiums apply. | Confirmed. Sections 8.2 and 8.3 provide BOSE-hired FTE salary benchmarks (Annual CTC in USD and INR). Agency/contractor rate benchmarks are maintained separately and delivered as a standalone 'Agency / Contractor Rate Benchmark' output (Section 14 row, Week 4). Niche-skill premiums are explicitly identified: SAP BTP / MuleSoft Architect / Senior SecOps add 15–25% to band midpoints; TinyML / Edge AI in GR&D context adds 20–30% above standard embedded bands. |
| Transition deliverables: include an insource/outsource recommendation by role family, wave plan, dependencies, and continuity risks. | Confirmed. Section 10.1 provides wave prioritisation by role family (Wave 1: standardised GBS; Wave 2: IT operational; Wave 3: complex/niche). Section 12.1 provides the insource vs. outsource recommendation using the Two-Axis Evaluation Matrix. Dependencies and continuity risks are captured in the RAID log and explicitly addressed in Section 10.3 (parallel-run period, KT obligations, and exit risk management). |
| Commercial deliverables: identify savings levers from location choice, rate renegotiation, contract-model changes, and insourcing decisions. | Confirmed. Section 15 and Section 15.2 (Commercial Assumptions) explicitly identify four savings lever categories: (1) Location choice, Hyderabad vs Bengaluru differential (15–18%) and India vs home-country savings (40–60%); (2) Rate renegotiation, volume consolidation and pyramid optimisation (Section 12.2); (3) Contract-model shift, from opaque outsourcing margins (25–40%) to transparent Cost + 15% (net 28–35% savings); (4) Insourcing, absorption of high-value vendor workloads into the GCC per Section 12.1 disposition framework. |

## Deliverables Matrix: ConglomerateIT Commitments

| Deliverable | Y/N | Timing | Format | ConglomerateIT Lead | [BOSE] Input Required |
| --- | --- | --- | --- | --- | --- |
| Delivery model business case | Y | Week 6 | Excel + PPT | Strategy Lead | Role demand, entity details |
| Entity activation plan & checklist | Y | Week 3 | PPT + Checklist | Legal/Compliance Lead | Entity documents |
| Operating model design | Y | Week 7 | PPT + Org chart | Org Design Lead | Reporting lines, governance intent |
| Talent and hiring plan | Y | Week 5 | Excel + PPT | Talent Lead (Amita Goyal) | JDs, headcount by role |
| Compensation benchmark: FTE | Y | Week 4 | Excel (GAP data) | Talent Lead | Final role list |
| Agency / contractor rate benchmark | Y | Week 4 | Excel (Rate Pulse) | Commercial Lead | Current vendor rate cards |
| Governance pack | Y | Week 6 | PPT + Templates | PMO Lead | Stakeholder map |
| GBS Control Tower design | Y | Week 7 | PPT + Dashboard spec | GBS Lead | SLA targets, process inventory |
| Transition roadmap & wave plan | Y | Week 8 | PPT + Excel | Transition Lead | Incumbent contract details |
| Launch readiness assessment | Y | Week 10 | Checklist + PPT | Program Lead | IT/security requirements |
| 90–180-day stabilization plan | Y | Week 8 | PPT + Excel | Transition Lead | SLA baselines |
| Role-level city talent benchmark | Y | Week 4 | Excel (GAP data) | Talent Lead | Confirmed role list |
| BOT / hybrid strategy | Y | Week 5 | PPT | Sourcing Lead | Niche role list, timeline constraints |
| Vendor consolidation strategy | Y | Week 6 | PPT + Excel | Commercial Lead | Incumbent scope and rates |
| Day 1 launch-readiness checklist | Y | Week 10 | Checklist | Program Lead | All workstreams confirmed |

| 6 | Commercial Response Requirements |
| --- | --- |

## Example on how Cost Plus Model works in India

| Cost Category | Line-Item Component | Monthly Cost (USD)* | Annual Cost (USD)* |
| --- | --- | --- | --- |
| 1. Talent Baseline | 15 Developers | $18,072 | $216,864 |
|  | Statutory Benefits, Insurance & Payroll Admin | $2,711 | $32,532 |
| 2. Hosted Facility | Dedicated, Branded Office Zone (Rent & Utils) | $3,614 | $43,368 |
|  | Physical Security, Housekeeping & Facilities | $904 | $10,848 |
| 3. Infrastructure | Dedicated Leased Lines, Firewalls & IT Support | $1,807 | $21,684 |
|  | Hardware Amortization (Laptops Passed as OpEx) | $1,084 | $13,008 |
| A. TOTAL COST BASELINE | Sum of All Direct Operational Expenses | $28,192 | $338,304 |
| B. MANAGEMENT FEE | ConglomerateIT Fee (15% of Line A) | $4,229 | $50,748 |
| C. TOTAL BILLING | Final Invoice Amount (Line A + Line B) | $32,421 | $389,052 |

# The above is a an example to demonstrate the pricing delivered to customer in a cost plus model as an assumption.

## Indicative savings against US baseline: 800 FTEs at steady state:

| Track | FTEs | US Fully Loaded Cost / FTE / Year | India Fully Loaded Cost / FTE / Year (incl. Cost+15%) | Annual Saving | Saving % vs US Baseline |
| --- | --- | --- | --- | --- | --- |
| GR&D Engineering | 320 | USD 150,000–180,000 | USD 48,000–63,000 | USD 28–38M / year | ~65–70% |
| IT | 320 | USD 120,000–150,000 | USD 32,000–46,000 | USD 24–35M / year | ~65–70% |
| GBS | 160 | USD 70,000–90,000 | USD 21,000–29,000 | USD 7–10M / year | ~65–70% |
| Total: 800 FTEs | 800 | USD 104–132M / year | USD 34–45M / year | USD 59–87M / year | ~63–68% |

India fully loaded cost includes: salary + PF + ESIC + gratuity provision + health insurance + PT + facilities + technology overhead + ConglomerateIT 15% margin. GCC saving vs US baseline computed at steady state (Month 22+).. Detailed 24-month cost model and analysis at RFP stage.

| Appendix A | Supplier Profile Template |
| --- | --- |

| Fields | Details |
| --- | --- |
| Legal company name | ConglomerateIT LLC USA |
| Headquarters | Hyderabad, India (Global HQ) · McKinney & Frisco, Texas, USA (North America HQ) |
| Year established | 2014 |
| Ownership structure | Founder-led private firm. No external investors. No competing client obligations. |
| Total employees globally | 290+ professionals across India and the US |
| India office locations | Hyderabad (primary HQ) · Bengaluru |
| US office locations | McKinney, TX · Frisco, TX |
| Relevant service lines | GCC Advisory & Setup · GCC Transformation · Talent Strategy & Acquisition · AI & Automation Advisory · Data Products · Technology & Global Operations |
| Primary contact (contracts) | Anuradha Warnakulasooriya, Strategy & Operations Anuradha@ConglomerateIT.com · Contracts@ConglomerateIT.com |
| GCC Practice Director: India | Bapu Jee BS, GCC Practice Leader India |
| GCC Advisory Board: India | Dr. Chakravarthy, Advisor & Strategist |
| GCC Advisory Board: USA | Shiva Kumar, GCC Practice Leader USA |
| Academia & Industry Advisor | Dr. Rajanikanth Aluvalu, Leading University India |
| Employer Branding Lead | Sumit Saxena, Digital Director · Ex Publicis |
| Recent M&A / org changes | None. No mergers, acquisitions, or restructuring. The same leadership team that founded ConglomerateIT in 2014 runs the firm today. |

| Appendix B | Reference Form |
| --- | --- |

| Contact | Title | Company | Engagement |
| --- | --- | --- | --- |
| Ashesh Kumar | President | India - Geo Disha Analytics Pvt Ltd USA - (Geo Disha INC) | Hyderabad GCC Setup: Product Development, Data, Digital and Business Analytics Centre |

| Appendix C | Participation & Dependencies Worksheet |
| --- | --- |

This worksheet defines what ConglomerateIT needs from Client to execute the programme on time. Every delay in the inputs listed here has a direct downstream impact on hiring, entity activation, or delivery. The "Critical if Delayed" column identifies what breaks first.

| Area | Client Inputs Needed | Expected Client Role / Level | Estimated Time Commitment | Timing | Critical if Delayed |
| --- | --- | --- | --- | --- | --- |
| Executive Sponsors ( | • City selection sign-off (Bengaluru for GR&D, Hyderabad for IT + GBS) • Delivery model approval per track (GCC vs BOT) • India entity strategy confirmation (Gurgaon WOS extension) • Budget and headcount authorisation for first wave hires • GR&D IP framework approval • Transfer Readiness criteria sign-off | CTO and/or COO Executive sponsor-level engagement required for all gateway decisions | 2–3 hrs / week Phases 1–2 (Months 1–8) 1 hr / week thereafter | Week 1 onwards City decision: Week 2 Model approval: Week 3 Budget sign-off: Week 4 | City decision past Week 2 cascades every downstream workstream, facilities, talent strategy, lab logistics, entity branch activation. Model decision delay means TP study cannot be scoped. First GR&D hire is blocked. |
| GR&D / Engineering Leaders | • GR&D role list with seniority levels and priority sequence (Day 1 vs Wave 2 vs Wave 3) • Active SoC platform list (Qualcomm QCC, Nordic nRF, TI, others), drives lab and partner engagement • Lab requirements: instrumentation, anechoic access, prototype handling protocols • Confirmation of which GR&D roles are Day 1 Client hires vs Wave 2 • Engineering workflows and tooling stack, required before onboarding design • IP classification framework: what is Highly Sensitive vs Sensitive vs Internal • Confirmation that IP assignment clause wording is acceptable before first hire | VP Engineering or CTO GR&D Must have authority to confirm role specs and IP framework without further escalation | 4–5 hrs / week Months 1–6 (active build) 2 hrs / week thereafter | Role list: Week 2 SoC platforms + lab requirements: Week 3 IP framework sign-off: Week 3 | GR&D role list delayed past Week 2 means audio DSP and wearable searches start late. These roles carry 70–90 day TTF. A 2-week delay = 2-week slip on first GR&D hires at minimum. IP framework not signed before hire = board IP mandate not met on Day 1. |
| IT Leaders | • IT role list by function: Salesforce, SAP, MuleSoft, OMS, DevOps, QA, Cloud, Cybersecurity, with seniority and wave priority • Current vendor landscape: which IT vendors are active, scope, contract end dates, and notice periods • Current rate cards for incumbent IT vendors (required for Rate Pulse benchmarking) • SAP landscape: ECC or S/4HANA, migration timeline if applicable • Salesforce clouds in active use: Commerce, Service, Marketing, Experience • MuleSoft: Client-managed or SI-managed; number of APIs and integration complexity • SOC: current structure, tooling, and geographic coverage • Technology standards: endpoint policy, identity management, DLP policy, before IT infrastructure setup | VP IT or Director IT Must be able to confirm vendor contracts and rate cards without Legal escalation for each item | 3–4 hrs / week Months 1–4 (planning phase) 2 hrs / week Months 4–12 | IT role list: Week 2 Vendor list + rate cards: Week 4 Technology standards: Week 5 | Incumbent vendor rate cards delayed past Week 4 push the Rate Pulse benchmarking and rebid strategy into Phase 2. Negotiation leverage decreases once vendors know a GCC is being built. Technology standards delay blocks IT infrastructure setup for both Bengaluru and Hyderabad offices. |
| HR / Talent | • Compensation philosophy: target percentile (P50, P60, P65) and variable pay structure for India • Existing India HR policies from Gurgaon entity: leave policy, gratuity structure, POSH framework • Hiring approval process and authority matrix, who approves offers at each seniority level • Offer turnaround SLA agreed: audio DSP and senior engineering roles cannot wait 5–7 days • ESOP or retention instrument availability for senior India hires • Onboarding programme scope, what ConglomerateIT builds, what Client owns • Background check vendor and standard for India hires | HR Director Must have authority to approve India-specific comp bands and offer terms without escalation for each hire | 4–5 hrs / week Months 1–3 (framework setup) 6–8 hrs / week Months 3–12 (active hiring) | Comp philosophy: Week 2 Approval matrix: Week 2 Offer SLA agreed: Week 3 India HR policies: Week 3 | Comp philosophy delay past Week 2 means the first job descriptions go live without a salary band. ConglomerateIT cannot post GR&D roles without knowing Client's target percentile. Offer turnaround slower than 48 hrs for senior engineering roles will cost specific candidates in a competitive market. |
| Finance / Tax / Legal | • Gurgaon entity documents: Certificate of Incorporation, MoA, AoA, existing statutory registrations • Current TP arrangements for Gurgaon entity, scope and which firm prepared them • Authorisation for Big 4 advisor to commence TP study for services delivery (IT, GBS, GR&D) • US international tax position: GILTI, Subpart F, Form 5471 filing obligations for new India operations • Appetite for intercompany cost-plus markup rates: GR&D (12–18%), IT services (10–15%), GBS (8–12%) • FEMA/RBI inward remittance structure sign-off for USD billing from US parent to ConglomerateIT • DPDP Act 2023 compliance scope, which data categories apply to India engineering operations • Legal sign-off on IP assignment clause wording before first GR&D hire | CFO (commercial) Tax Director (TP + GILTI) General Counsel (entity docs, IP, DPDP) All three must be engaged by Week 1, not sequentially | 3–4 hrs / week Months 1–3 (TP, entity, DPDP) 1–2 hrs / week thereafter | Entity docs: Week 1 Big 4 TP engagement: Week 1 TP markup rates: Week 2 IP clause sign-off: Week 3 ICA execution: before first hire | TP study not commissioned by Week 1 means PE exposure begins on first GR&D hire. Cannot be remediated retroactively. ICA not executed before first hire = every payment from US to India is unstructured. Indian tax authority will challenge it. DPDP framework not in place before first engineering hire = engineering data classification is retroactive. Board IP mandate is not met. |
| Procurement / PMO | • Full incumbent vendor list: name, scope, headcount delivering for Client, city, contract value, and expiry date • Current rate cards and SLA frameworks for all IT and GBS incumbent vendors • Contractual notice periods and transition support obligations for each vendor • Internal procurement governance: what requires formal tender vs direct award, approval thresholds • ConglomerateIT engagement contract: MSA, SOW, and NDA, all to be executed by Week 2 • Programme governance preferences: steering cadence, escalation paths, reporting formats • PMO tooling: does Client have a preferred project management or RAID logging platform | VP Procurement PMO Lead Procurement must have authority to share vendor contracts without a separate legal review gate for each document | 3–4 hrs / week Months 1–3 (vendor assessment and contracts) 2 hrs / week ongoing | MSA/SOW/NDA: Week 2 Vendor list: Week 3 Rate cards: Week 4 Governance model agreed: Week 4 | MSA and SOW not executed by Week 2 means ConglomerateIT cannot mobilise its team or incur costs on Client's behalf. Programme start date moves. Vendor rate cards delayed past Week 4 mean the incumbent assessment and rebid strategy are not ready before incumbents learn the GCC is being built, negotiation leverage is lost. |
| GBS / Portugal Operations | • GBS process catalogue: all active processes, platforms (Blackline, Ariba, AA, PMG), volume metrics, and exception rates • Portugal team structure: headcount, roles, seniority, and what each person currently owns • Division of labour decision: which processes stay in Portugal, which move Wave 1, which move Wave 2 • Portugal GBS leadership availability for Phase 1 process ownership workshops, minimum 4 sessions of 2 hrs each • Blackline, SAP Ariba, Automation Anywhere, PMG: license ownership, version, current usage volumes • Automation Anywhere: how many bots running, who manages them, which processes they cover • Current SLA framework for GBS processes, the baseline against which India performance will be measured | VP GBS or COO-org lead Portugal GBS lead must be a co-designer of the transition, not a recipient of a decision made elsewhere | 4–6 hrs / week Months 1–4 (process ownership design) 2 hrs / week Months 4–12 (Wave 1 oversight) | Process catalogue: Week 3 Ownership matrix sessions: Weeks 3–6 Division of labour agreed: Week 8 SLA baselines: Week 6 | Without the division of labour decision by Week 8, the India GBS team cannot be scoped. ConglomerateIT will hire into a role definition that does not match the actual work. Portugal non-participation in the process ownership workshops results in a transition that Portugal resists. Wave 1 delays by 6–8 weeks minimum. SLA baselines not established before India go-live means performance cannot be measured in the first 90 days. |

Note: All timing references are from programme start (Week 1 = first week of formal engagement). The "Critical if Delayed" column reflects ConglomerateIT's experience across comparable GCC engagements. Items marked Week 1 or Week 2 are on the critical path to the first hire and cannot slip without extending the overall programme timelines.

| Appendix D | Indicative Launch Workstreams Checklist |
| --- | --- |

| Workstream | Included? | Comments / Assumptions |
| --- | --- | --- |
| City selection | Yes | Bengaluru confirmed for GR&D Engineering. Hyderabad confirmed for IT and GBS. Selection based on ConglomerateIT's proprietary 40-factor scoring model covering talent depth, cost, attrition, real estate, GR&D ecosystem (SoC vendors, anechoic access, KIA prototype logistics), and regulatory maturity. City scoring model and full factor breakdown provided as a Phase 1 deliverable. Assumption: Client confirms city selection by Week 2 of programme. Dual-city model (Bengaluru + Hyderabad) is included in scope. |
| Entity setup | Yes | No new entity incorporation required. ConglomerateIT activates its own Telangana operating entity for the IT and GBS BOT tracks. Client's existing Gurgaon WOS (CIN U74899HR1995PTC075400, est. 1995) is extended into Karnataka and Telangana via branch registrations during Phase 5, ahead of the Month 24 transfer. For GR&D, Client's existing entity operates the Karnataka branch from Day 1. Assumption: Entity documents (MoA, AoA, existing registrations) provided by Client Finance/Legal in Week 1. TP study commissioned via Client's Big 4 advisor by Week 1. |
| Tax / finance setup | Yes | Transfer Pricing study for three service categories: GR&D Engineering (12–18% markup), IT services (10–15%), GBS process services (8–12%). Intercompany Services Agreement executed before first hire. India TP Safe Harbour alignment for Cost+15% open-book model. GST: export-of-services (IGST zero-rated) registration in Karnataka and Telangana. FEMA/RBI inward remittance structure for USD billing from Client US to ConglomerateIT. DPDP Act 2023 compliance assessment. US tax position (GILTI, Subpart F, Form 5471), flagged to Client's US counsel; not in ConglomerateIT scope to execute. Assumption: Client's Big 4 advisor engaged by Week 1. TP markup rates approved by Client Tax Director by Week 2. |
| Talent acquisition | Yes | Full talent acquisition across all three tracks via ConglomerateIT's GAP platform and curated talent pipelines. GR&D Engineering: niche search via Harman International, Qualcomm QCC, Dolby India, and IISc alumni networks, audio DSP, wearable BT audio, RTOS, TinyML, mobile app (BT/WiFi stack). IT: Salesforce, SAP, MuleSoft, DevOps, cybersecurity, QA, Hyderabad market. GBS: Blackline, SAP Ariba, Automation Anywhere, PMG specialists, Hyderabad market. Executive search for India Site Leader and GR&D Engineering Lead from Week 1. Assumption: Client comp philosophy (target percentile) confirmed by Week 2. Offer approval SLA of 48 hrs agreed for senior GR&D roles. Executive search fees for Site Leader and GR&D Lead are separate from advisory fee. |
| Office / facilities setup | Yes | Bengaluru (GR&D): Managed/serviced workspace (15–25 seats) in Months 1–3 in Bengaluru tech park (RMZ, Bagmane, or Prestige ecosystem). Flex/co-working with dedicated GR&D lab bay from Month 3. Permanent office from Month 9 (150–200 seats). Hyderabad (IT + GBS): Managed workspace (30–50 seats) Months 1–3. Flex expansion Months 3–8. Permanent from Month 9. Lab bay requirement: dedicated, locked, VLAN-isolated from Month 4 for GR&D. Assumption: Facilities costs (lease, fit-out, furniture) are Client costs, ConglomerateIT advises and coordinates. Client confirms fit-out standards and brand guidelines by Week 5. |
| IT / security setup | Yes | Endpoint provisioning per Client MDM standard before Day 1 access. Identity and access management: SSO, MFA, zero-trust principles applied from Day 1. Network: dual-carrier MPLS, SD-WAN for business continuity. GR&D lab on isolated VLAN with dedicated bandwidth and DLP controls. SOC integration: India team connected to Client global SOC by Month 3. DPDP Act 2023 compliance: data classification, cross-border transfer documentation, engineering data controls (audio algorithms and firmware classified Highly Sensitive from Day 1). Assumption: Client IT team provides technology standards, endpoint policy, and identity management requirements by Week 5. Client CISO approves security architecture before endpoint deployment. |
| Transition planning | Yes | Three-wave transition model for IT and GBS. Wave 1 (Phase 2, Months 3–8): Order Management, Master Data (PMG), Ariba PO processing, Automation Anywhere cash application, sell-through normalisation. Wave 2 (Phase 3–4, Months 8–18): Blackline reconciliations (standardised), contract administration, analytics, PMO reporting. Wave 3 (Phase 4–5, Months 14–22): Remaining complex GBS and senior IT roles. Each wave gated on Control Tower Horizon 1 readiness data, not a calendar date. Knowledge transfer protocol: 2–4 week shadow period per process, KT completeness score ≥95% before handoff. Assumption: Portugal GBS leadership participates in 4 process ownership workshop sessions in Weeks 3–6. Division of labour agreed by Week 8. |
| PMO / governance | Yes | ConglomerateIT establishes and runs PMO from Week 1. Five governance forums: (1) Ramp War Room, weekly, Months 1–18; (2) Delivery Governance, bi-weekly; (3) Executive Steering Committee, monthly; (4) Transformation Council, monthly; (5) Transfer Readiness Board, quarterly from Month 6. RAID log maintained from Week 1. Transfer Readiness Index (TRI) published quarterly from Month 6 across six dimensions: Leadership, Process, Infrastructure, People, Governance, Commercial. Transfer at Month 24 is gated on all six TRI dimensions green, not a calendar obligation. Assumption: Client executive sponsor (CTO or COO level) available for weekly steering in Months 1–6, bi-weekly thereafter. |
| Launch readiness / stabilisation | Yes | Launch readiness gate before each wave: facilities operational, IT infrastructure tested, payroll cycle confirmed, first cohort onboarded, governance forums live. Hypercare model: Days 1–30 (ConglomerateIT on-site daily, no SLA enforcement on new hires), Days 31–60 (SLA measurement begins, performance coaching), Days 61–90 (SLA enforcement, weekly advisory support). Stabilisation continues through each hiring wave, not a one-time event. Transfer Readiness Index tracks stabilisation across all six dimensions quarterly. Assumption: SLA baselines agreed between ConglomerateIT and Client before each wave goes live. Hypercare scope confirmed per wave. |
| Agency strategy / incumbent assessment | Yes | ConglomerateIT Rate Pulse benchmarking applied to all active incumbent IT and GBS vendors. Four-step assessment: (1) Service quality audit, SLA performance, hidden cost identification; (2) Strategic dependency mapping, knowledge concentration and contractual lock-in; (3) Rate benchmarking, current rates vs Rate Pulse India benchmarks by role and city; (4) Exit risk scoring, Low/Medium/High per vendor based on notice period, knowledge transferability, replacement timeline. Typical finding: 15–25% rate headroom in mature IT services contracts at Client's scale. Assumption: Client provides full incumbent vendor list, rate cards, and contract end dates by Week 4. Procurement team has authority to share these without a separate legal review gate per document. |
| BOT / incubate-to-captive option | Yes | ConglomerateIT's core commercial model for the IT and GBS tracks (480 people, Hyderabad) is BOT with Basic-fee transfer at Month 24. All employees on ConglomerateIT payroll during the BOT period. USD billing from Client US to ConglomerateIT, no India billing during engagement. Open-book Cost+15%: every cost component (salaries, PF/ESIC, facilities, technology, overheads) itemised in monthly invoice with margin line separately identified. Basic transfer fee at Month 24, profit earned monthly, not at exit. Employment contracts novated to Client's India entity at transfer: tenure intact, benefits preserved, PF UAN records transferred, payroll migrated in one cycle. ConglomerateIT has executed this model twice, both clients transferred in one payroll cycle, zero attrition through the rebadge event. |
| Rate benchmarking / negotiation support | Yes | Rate Pulse platform provides India IT and GBS rate intelligence by role, city, and technology, updated bi-annually from active ConglomerateIT commercial engagements. Benchmarking covers: (a) FTE permanent salary bands (P50, P60, P65 GCC positioning) by role and city; (b) Contractor/agency rate benchmarks, separately from FTE, including agency margin (typically 15–25%); (c) Niche skill premiums identified by role (audio DSP: +18–27% above P65; TinyML: +15–25%; SAP S/4HANA Architect: +10–18%). Negotiation support: structured rebid approach for IT and GBS incumbents, commercial lever identification, and contract model recommendations. Assumption: Rate benchmarking output is a Phase 1 deliverable (Week 4). Client Procurement participates in strategy sessions. |
| Role-level city talent benchmark | Yes | GAP platform provides role-level talent benchmarks for all Client role families across Bengaluru and Hyderabad. Covers: FTE permanent salary bands (base + variable), time-to-fill (median and P90), attrition rates, and niche premium flags. GR&D track: audio DSP (30–38L Bengaluru), wearable/TWS BT audio (25–34L), RTOS/firmware (20–30L), TinyML (22–32L), mobile app (18–28L). IT track: Salesforce Architect (22–30L Hyderabad), SAP Functional (16–24L), MuleSoft Lead (20–28L), DevOps Lead (18–26L), Cybersecurity (18–28L). GBS track: Order Management/Master Data (8–14L), GBS PMO (16–22L), Blackline Specialist (14–20L), Automation Anywhere Developer (16–24L). Talent benchmarks are separated from agency/contractor rates. Niche premiums identified by role. Data source: ConglomerateIT GAP platform, Q1 2026. INR/USD 84. |
| Transition wave planning | Yes | Detailed wave plan provided as a Phase 1 deliverable (Week 8). See Appendix G for role-level wave assignments. Three-wave structure: Wave 1 (Phase 2, Months 3–8), rule-based, high-volume GBS and IT operations; Wave 2 (Phase 3–4, Months 8–18), moderate complexity GBS and specialist IT; Wave 3 (Phase 4–5, Months 14–22), complex GBS and senior IT architects. Each wave includes: insource/outsource recommendation by role family, knowledge transfer dependencies, continuity risk assessment, and parallel-run period. Wave gate criteria: Transfer Readiness Index Process dimension green, SLA stable for 60+ days, shadow period complete, Portugal GBS lead sign-off. Assumption: Client confirms role-level wave priority by Week 6. Portugal GBS division of labour agreed by Week 8. |

| Appendix E | Risks and Assumptions Log |
| --- | --- |

| Category | Risk / Assumption | Impact if Realized | Likelihood | Mitigation Approach | Owner | ConglomerateIT Dependency | Client Dependency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Location | City decision delayed past Week 2 | All downstream workstreams (facilities, talent, lab, entity branch) cascade. Every week of delay = week of programme slip. | High | Hard gate in PMO plan. City assessment delivered Week 2 to enable rapid decision. Executive Steering escalation if not confirmed. | ConglomerateIT | ConglomerateIT PMO Lead | City selection confirmed by Client executive sponsor by end of Week 2. |
| Location | Assumption: Bengaluru for GR&D, Hyderabad for IT + GBS | If Client changes city preference post-Week 2, facilities, lab logistics, talent pipelines, and entity branch activation all restart. | Low | Dual-city model scored and recommended in Phase 1. Assumption stated explicitly in all programme planning. | ConglomerateIT + Client | ConglomerateIT proceeds on Bengaluru + Hyderabad basis unless Client formally changes this by Week 2. |  |
| Talent | Audio DSP and wearable BT audio talent scarcity in Bengaluru | Wave 1 GR&D hiring extends 8–12 weeks beyond plan. First 30 engineers in seat later than Month 6. | High | Niche search via Harman, Qualcomm QCC, Dolby alumni networks activated Week 2. GR&D Engineering Lead search starts Week 1. Compensation at above-P65 approved pre-launch. | ConglomerateIT + Client | GR&D Engineering Lead in seat by Month 3. |  |
| Talent | India Site Leader hire takes longer than 10 weeks | Leadership vacuum delays hiring pipeline, governance setup, and employer brand activation. | Medium | Executive search firm engaged Week 1. Parallel interim: ConglomerateIT SVP holds site leadership accountability until permanent hire is in seat. | ConglomerateIT + Client | Executive search firm shortlist delivered by Week 6. |  |
| Talent | Assumption: India compensation benchmarks remain stable (Q1 2026 data) | If market moves significantly, compensation bands in proposal may need revision. | Low | GAP platform updated quarterly. Annual increment commitment of 8–10% factored into open-book cost model. | ConglomerateIT + Client | GAP platform data updated if market shifts >8%. |  |
| Legal / Tax | TP study not commissioned before first GR&D hire | PE exposure for Client US parent from Day 1. Cannot be remediated retroactively. Indian tax authority will challenge unstructured US-to-India payments. | Medium | TP study scoped and Big 4 advisor engaged as Week 1 deliverable. ICA drafted before first hire. | ConglomerateIT + Client | TP study scope delivered to Client by Week 2. |  |
| Legal / Tax | Existing Gurgaon entity compliance issues surface during entity review | Delays Karnataka and Telangana branch activation. May require entity remediation before first hire. | Low | Entity compliance review completed by Week 3. Any issues surfaced and escalated immediately with remediation plan. | ConglomerateIT + Client | Entity compliance checklist completed by Week 3. |  |
| Legal / Tax | Assumption: India TP Safe Harbour applies to Cost+15% model | If CBDT modifies Safe Harbour notification, markup rates may need adjustment. | Low | Cost+15% is within current Safe Harbour range (IT services). TP study documents ALP basis independent of Safe Harbour. | ConglomerateIT + Client | Monitoring of CBDT notifications. Alert to Client if rules change. |  |
| Facilities | Grade A tech park availability in Bengaluru/Hyderabad within programme timeline | Managed workspace cost increases if permanent office delayed. GR&D lab bay not available for Month 4 target. | Low | LOI on 2–3 preferred tech parks (RMZ, Bagmane, Prestige in Bengaluru; HITEC City, Gachibowli in Hyderabad) placed in Phase 1. Flex/managed workspace confirmed as contingency. | ConglomerateIT + Client | Facilities assessment delivered Week 4. LOI by Week 6. |  |
| Facilities | GR&D lab build-out delayed (instrumentation, anechoic access) | GR&D engineers in seat without lab access. Productivity impact in Months 4–6. | Low | Commercial anechoic access (CTTC, Bengaluru) booked in Phase 1. Instrumentation rental arranged (Keysight India, R&S India, Audio Precision India). Portable RF cage as interim. | ConglomerateIT + Client | Lab logistics plan and vendor contacts delivered Week 4. |  |
| Technology / Security | Client IT provisioning timelines slip (endpoints, network, SOC) | Day 1 access delayed. Productivity loss in first hiring cohort. GR&D engineers cannot access engineering tools. | Medium | Provisioning plan agreed in Phase 1. Managed device pool as bridge. GR&D lab on isolated VLAN from Day 1 regardless of broader office network status. | ConglomerateIT + Client | IT setup plan delivered Week 5. |  |
| Technology / Security | DPDP Act 2023 compliance requirements stricter than anticipated | Engineering data classification or cross-border transfer restrictions create operational friction for GR&D workflows. | Low | DPDP impact assessment delivered as Phase 1 deliverable. Engineering data classification framework agreed before first hire. | ConglomerateIT + Client | DPDP assessment delivered Week 6. |  |
| Transition | Portugal GBS non-participation in process ownership workshops | Wave 1 GBS transition delayed by 6–8 weeks. India GBS team scoped incorrectly. Portugal resistance increases. | Medium | Portugal GBS leadership co-designs ownership matrix, not receives it. Joint GBS Leadership Council established from Month 4. Wave gate requires Portugal sign-off. | ConglomerateIT + Client | ConglomerateIT facilitates all ownership workshops. |  |
| Transition | Incumbent vendor knowledge concentration creates transition risk | Service disruption during wave transitions. Critical knowledge exits with departing vendor staff. | Medium-High | KT protocol with minimum 2–4 week parallel-run period per process. Contractual KT obligations enforced via Procurement. Dependency mapping complete by Week 4. | ConglomerateIT + Client | KT protocol and dependency map delivered Week 5. |  |
| Partner / BOT Model | BOT employee quality below GR&D engineering standard (if BOT used for any GR&D roles) | Employer brand impact. IP exposure window during non-captive period. | N/A, mitigated by design | GR&D track is direct Client payroll from Day 1. No BOT model for any engineering role. This risk does not apply to the GR&D track. | ConglomerateIT + Client | N/A |  |
| Partner / BOT Model | ConglomerateIT Telangana BOT entity operational readiness | IT and GBS BOT delivery delayed if entity setup takes longer than planned. | Low | ConglomerateIT begins entity incorporation at programme start. Entity operational within 6–8 weeks. Managed workspace contracted independently of entity status. | ConglomerateIT | BOT entity operational by Month 2. |  |
| Timeline / Governance | Client decision speed slower than assumed | All workstreams slip. City decision, comp philosophy, vendor rate cards, entity docs, all on critical path. | Medium-High | Decision log with named owner and due date for every decision. Escalation protocol agreed Week 1. Ramp War Room surfaces blockers weekly. | ConglomerateIT + Client | Escalation plan and decision log live from Week 1. |  |
| Timeline / Governance | Assumption: 800-person headcount target is confirmed and budgeted | If headcount changes materially post-Phase 1, talent strategy, facilities plan, and cost model all require revision. | Low | ConglomerateIT programmes are designed for phased ramp, changes at phase boundaries can be absorbed more easily than mid-wave. | ConglomerateIT | Phase gate reviews allow scope adjustment. |  |

| Appendix G | Role and Transition Wave Worksheet |
| --- | --- |

ConglomerateIT has pre-populated this worksheet based on the RFI scope. Client should review and confirm or amend role priorities, wave assignments, and headcount estimates before RFP. All salary data from ConglomerateIT GAP platform, Q1 2026.

| Role Family | Launch Wave | City | Likely Source | Salary Band (INR p.a.) | Key Dependencies / Notes |
| --- | --- | --- | --- | --- | --- |
| Audio DSP Engineer (ultra-low-latency pipeline) | Wave 1 (Month 4–8) | Bengaluru (only) | Direct Client hire, niche search Harman, Dolby, Qualcomm QCC alumni | 30–38L | Scarce. TTF: 70–90 days. Above-P65 comp required. Search starts Week 2. No BOT, IP mandate. |
| Wearable / TWS BT Audio Engineer | Wave 1 (Month 5–9) | Bengaluru (only) | Direct Client hire Qualcomm QCC alumni primary source | 25–34L | Moderate scarcity. QCC alumni network. TTF: 60–80 days. IP assignment Day 1. |
| Embedded Firmware Engineer (RTOS / FreeRTOS / Zephyr) | Wave 1 (Month 4–8) | Bengaluru (primary) | Direct Client hire Aerospace, IoT, automotive ecosystem | 20–30L | Good pool in Bengaluru. TTF: 45–60 days. Strongest pool outside automotive. |
| TinyML / Edge AI Engineer (battery-optimised inference) | Wave 2 (Month 8–14) | Bengaluru (only) | Direct Client hire IISc, Google AI, Intel AI labs alumni | 22–32L | Emerging specialisation. TTF: 60–80 days. IISc pipeline key for junior roles. |
| Mobile App Engineer (iOS/Android, BT/WiFi stack) | Wave 1 (Month 4–8) | Bengaluru / Hyderabad | Direct Client hire Good availability both cities | 18–28L | Swift, Kotlin, KMP, Flutter all available. BT/WiFi stack experience adds premium. |
| Sensor Integration / Sensor Fusion | Wave 2 (Month 8–14) | Bengaluru | Direct Client hire IoT and wearable ecosystem | 18–26L | Moderate availability. Wearable IoT ecosystem in Bengaluru. |
| QA / Validation Engineer (audio and embedded) | Wave 1 (Month 6–10) | Bengaluru | Direct Client hire or BOT bridge Embedded test background | 14–22L | Audio validation niche but teachable. Embedded test background key selector. |
| DevOps / CICD (embedded, AI-augmented) | Wave 1 (Month 5–9) | Bengaluru | Direct Client hire or BOT bridge | 16–24L | AI-assisted CICD growing in Bengaluru. Good availability. |
| GR&D Engineering Lead (India) | Phase 1 (Month 2–3) | Bengaluru | Executive search Direct Client hire | 50–75L | Anchor hire. Holds lab culture, SoC partner relationships, hiring pipeline. Starts Month 2. |
| Salesforce Architect / Lead (Commerce + Service Cloud) | Wave 1 (Month 5–9) | Hyderabad | Direct Client hire | 22–30L | SFCC and Service Cloud priority. SF Architect is Day 1 direct hire; developers via BOT bridge. |
| SAP Solution Architect (S/4HANA / ECC) | Wave 1 (Month 5–9) | Hyderabad | Direct Client hire | 24–34L | S/4HANA migration experience commands 15% premium over ECC. Senior architect Day 1 direct hire. |
| SAP Functional Consultant (SD / MM / FI / CO) | Wave 1–2 | Hyderabad | Direct hire + BOT bridge | 16–24L | Good availability in Hyderabad. ABAP developers via BOT. Functional via direct hire. |
| MuleSoft / Integration Lead | Wave 1 (Month 5–9) | Hyderabad | Direct Client hire Lead is direct; developers BOT | 20–28L | Scarce in Hyderabad. TTF: 50–70 days. Lead is direct hire; integration developers via BOT. |
| OMS Tech Lead / Developers | Wave 1 (Month 5–9) | Hyderabad | Direct hire + BOT bridge | 18–26L | Lead direct hire. OMS developers strong BOT candidate. |
| QA / Test Automation | Wave 1 (Month 4–8) | Hyderabad | BOT bridge (volume) | 14–20L | High volume. Strong BOT candidate. Good Hyderabad availability. |
| DevOps / Platform / Scrum Masters | Wave 1–2 | Hyderabad | Direct hire + BOT bridge | 18–26L | DevOps Lead direct hire. Platform engineers via BOT. Good Hyderabad availability. |
| Cloud / Infrastructure Engineer | Wave 2 (Month 8–14) | Hyderabad | Direct hire + BOT | 18–26L | Good cloud availability in Hyderabad. IT Security Lead Day 1 direct hire. |
| Cybersecurity / SecOps (mid-senior) | Wave 2 (Month 8–14) | Hyderabad | Direct Client hire Niche search | 18–28L | Scarce. TTF: 60–80 days. Premium skill. CISO-connected search. |
| IT Head (India) | Phase 1 (Month 2–3) | Hyderabad | Direct Client hire Executive search | 45–65L | Day 1 leadership hire. Owns platform decisions and security posture from Day 1. |
| Order Management / Exception Handling (PMG) | Wave 1 (Month 3–8) | Hyderabad | BOT bridge (Wave 1) Direct hire at transfer | 8–14L | Core Day 1 GBS scope. Rule-based, high-volume. Transfers cleanly. Control Tower Horizon 1 confirms readiness. |
| Customer + Product Master Data (PMG) | Wave 1 (Month 3–8) | Hyderabad | BOT bridge (Wave 1) Direct hire at transfer | 8–14L | Same profile as Order Management. Standardised process. Strong BOT candidate. |
| SAP Ariba: Operational PO Processing + AP | Wave 1 (Month 3–8) | Hyderabad | BOT bridge Direct hire at transfer | 10–16L | Ariba skills well-represented in Hyderabad. High-volume, portal-driven. Transfers cleanly. |
| Automation Anywhere Developer / Operator | Wave 1 (Month 3–8) | Hyderabad | BOT bridge Direct hire at transfer | 16–24L | Cash application and sell-through normalisation. AA A360 skills available in Hyderabad. |
| Blackline Reconciliation Specialist (standardised) | Wave 2 (Month 8–14) | Hyderabad | Direct hire (after Wave 1 stability) | 14–20L | Wave 2 only: India team needs 6–12 months operational maturity first. Gated on TRI Process dimension green. |
| Contract Administration / Customer Communications | Wave 2 (Month 8–14) | Hyderabad | Direct hire | 10–16L | Moderate complexity. Requires shadow period with Portugal team before handoff. |
| GBS Analytics / Data Support | Wave 2 (Month 8–14) | Hyderabad | Direct hire | 14–20L | Builds toward Control Tower Horizon 2. Analytics skills available in Hyderabad. |
| GBS PMO / Process Excellence | Wave 1–2 | Hyderabad | Direct hire (senior roles) | 16–22L | Senior roles direct hire. Process excellence supports Control Tower design. |
| Head of GBS (India) | Phase 1 (Month 2–3) | Hyderabad | Direct Client hire Executive search | 40–60L | Day 1 leadership. Co-chairs Joint GBS Leadership Council with Portugal GBS lead from Month 4. |
| India Site Leader | Phase 1 (Month 1–2) | Bengaluru or Hyderabad | Executive search Direct Client hire | 65–95L | Anchor hire for entire programme. Full P&L accountability. Starts Month 1. Search engaged Week 1. |
| HR Lead: India | Phase 1 (Month 1–2) | Hyderabad | Direct Client hire | 25–35L | In seat before first hiring wave. Owns India HR policies, payroll, and onboarding. |
| Finance Lead: India | Phase 1 (Month 2–3) | Hyderabad | Direct Client hire | 25–35L | Manages open-book cost-plus reporting, statutory filings, and monthly invoice pack. |
| IT Security / Infrastructure Lead | Phase 1 (Month 3–4) | Bengaluru | Direct Client hire | 35–50L | Manages GR&D lab VLAN, DLP controls, SOC integration, and engineering data classification. |
| Facilities / Workplace Manager | Phase 1 (Month 1–2) | Hyderabad (dual-city) | Direct Client hire or BOT support | 15–22L | Coordinates managed workspace, permanent office selection, lab setup in both cities. |

Note: FTE salary bands at P55–P65 GCC positioning. Contractor/agency rates are 20–35% above FTE equivalent due to agency margin (15–25%). Niche premiums: audio DSP +18–27% above P65; TinyML +15–25%; SAP S/4HANA Architect +10–18%; MuleSoft Lead +8–15%. All data: ConglomerateIT GAP platform Q1.

ConglomerateIT

Global R&D Engineering India Enablement

Additional Information

# Executive Summary

ConglomerateIT welcomes the opportunity to respond to Client's Global R&D Engineering India Enablement Addendum. We understand that Client is evaluating the feasibility of establishing an India-based engineering presence capable of supporting specialized GR&D capabilities: specifically in audio DSP, wearable technology, embedded systems, wireless (BT/WiFi), TinyML, edge AI inference, and Mobile App engineering, while keeping this presence fully complementary to the existing IT and GBS delivery model.

# Understanding Client's GR&D Engineering Needs in India

ConglomerateIT understands that Client designs and develops premium audio and wearable consumer electronics products where performance differentiation is driven by software and firmware, not just hardware selection. This creates a specific and demanding India talent profile that goes well beyond generalist embedded hiring.

The capabilities Client seeks: ultra-low-latency audio DSP, Cadence Design Tool expertise, TinyML on constrained devices, TWS Bluetooth audio stacks, FreeRTOS/Zephyr firmware, battery-optimized AI inference, and full-stack Mobile App development with BT/WiFi expertise: represent the upper tier of India's embedded and systems engineering talent market. These roles exist in India at meaningful depth but require targeted sourcing, specific screening frameworks, and realistic ramp timelines.

# Role Architecture and Recommended Hiring Sequence

The table below summarizes the engineering roles we recommend Client prioritize for India hiring, along with experience levels, reporting structure guidance, and recommended sequencing:

| Role Family | Level | Sequence | Model | Notes |
| --- | --- | --- | --- | --- |
| Audio DSP Engineer | Senior / Staff | Day 1 | Direct Hire | Core IP role; must be Client-employed from Day 1. Sourced from Harman, Dolby India, Qualcomm Audio group, Samsung R&D. |
| Embedded Firmware / BT Audio | Mid / Senior | Day 1 | Direct Hire | TWS stack, BT audio integration, Bluetooth SIG profiles. Strong pool in Bengaluru near QCC and MediaTek centres. |
| Mobile App Engineer (iOS/Android) | Mid / Senior | Day 1 | Direct Hire | Swift, Kotlin, KMP, Flutter; BT/WiFi stack expertise. AI-assisted code generation and CI/CD pipeline automation expected. Hyderabad recommended. |
| RTOS / Embedded Linux Engineer | Senior / Staff | Month 1-3 | Direct / Partner | FreeRTOS, Zephyr, board bring-up, BSP, firmware CI/CD. Hyderabad deep pool; Bengaluru for SoC-adjacent roles. |
| Wearable / Low-Power Systems Engineer | Senior | Month 1-3 | Partner Ramp | Sensor integration, sensor fusion, power/performance trade-offs. Scarce niche; partner-supported launch with conversion pathway. |
| TinyML / Edge AI Engineer | Senior / Staff | Month 3-6 | BOT / Partner | Model quantization, on-device inference, battery-aware ML. Small talent pool; recommend BOT through university partnerships and Bengaluru AI ecosystem. |
| Audio Validation / Lab Engineer | Mid | Month 1-2 | Direct Hire | Acoustic measurement, audio pipeline validation, instrumentation operation. Bengaluru preferred given lab access. |

# City-by-City Compensation, Time-to-Fill, and Attrition

All figures below are approximate mid-market ranges based on ConglomerateIT's current placement data (2025-2026). Premium/scarce roles may be 20-30% above these bands.

| Role | City | Salary Band (INR L/yr) | USD Equiv. | Time to Fill | Difficulty | Attrition Risk | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Audio DSP Engr | Bengaluru | 45–75L | $54–90K | 10–14 wks | High | Moderate |  |
| Audio DSP Engr | Hyderabad | 38–65L | $45–78K | 12–16 wks | High | Moderate |  |
| BT Firmware Engr | Bengaluru | 30–55L | $36–66K | 8–12 wks | Moderate-High | Moderate |  |
| BT Firmware Engr | Pune | 28–50L | $34–60K | 10–14 wks | Moderate | Low-Mod |  |
| Mobile App (iOS/Android) | Hyderabad | 22–45L | $26–54K | 6–10 wks | Moderate | Moderate |  |
| Mobile App (iOS/Android) | Bengaluru | 25–50L | $30–60K | 6–8 wks | Moderate | Moderate-High |  |
| RTOS/Embedded Linux | Bengaluru | 28–52L | $34–62K | 8–12 wks | Moderate | Moderate |  |
| RTOS/Embedded Linux | Hyderabad | 25–48L | $30–58K | 8–12 wks | Moderate | Low-Mod |  |
| TinyML / Edge AI | Bengaluru | 35–65L | $42–78K | 14–20 wks | Very High | High | Niche |
| Wearable Systems Engr | Bengaluru | 30–58L | $36–70K | 12–18 wks | High | Moderate |  |

## Recruiting Channels and Candidate Assessment

For the GR&D role families above, ConglomerateIT uses the following sourcing channels:

- SoC Vendor Alumni Networks: Qualcomm, MediaTek, Texas Instruments, Nordic Semiconductor, Cirrus Logic India engineering centres: primary source for audio DSP and BT firmware talent.

- Industry Engineering Communities: Embedded Related, Bluetooth SIG India chapter, IEEE Signal Processing Society, NASSCOM Engineering R&D forum.

- University Partnerships: IISc (audio/signal processing PhD pipeline), IIT Madras (embedded systems), IIT Bombay (wireless), BITS Pilani Goa (mobile/firmware), IIIT Hyderabad (AI/ML on edge devices).

- Specialist Niche Search: For TinyML and low-power AI inference roles, ConglomerateIT partners with Accord Manpower (Bengaluru) and Elite recruits (Chennai) for R&D-specific retained search.

- Technical Assessment Platform: Hacker Rank (embedded C/C++, BT stack modules), custom DSP algorithm design exercises co-developed with Client, and lab-oriented evaluation for validation engineers.

## GR&D Hiring Sequenced with IT and GBS Setup

ConglomerateIT recommends a parallel-track model where GR&D hiring begins at Month 2 of IT/GBS setup: not sequentially after GBS is operational. The shared India entity structure, HR operations, payroll, and facilities established for IT/GBS provide immediate administrative infrastructure that GR&D engineers can onboard into without duplication. Engineering-specific additions (lab space, secure workstations, development sample handling) are layered on top.

## Lab and Workspace Setup Experience

ConglomerateIT has supported engineering workspace and lab set-up for three product engineering GCCs in India in the past four years, including a consumer IoT company establishing antenna and RF characterization capability in Bengaluru, and a medical device OEM setting up EMC pre-compliance lab in Pune. We understand the India-specific constraints around import licensing, customs clearance, and calibration certification that differ materially from US or EU lab setup.

## Import/Export Routes for Development Samples and Equipment

| City | Recommended Route | Customs Broker | Expected Lead Time | Key Considerations |
| --- | --- | --- | --- | --- |
| Bengaluru | Kempe Gowda Intl Airport (BLR): air freight preferred for prototypes | Crown Worldwide / DHL Express | 7–14 business days (air); ETA approval 3–5 days prior | STPI/SEZ registration recommended for duty deferral; avoid sea for time-sensitive proto boards |
| Chennai | Chennai Seaport + Chennai Intl Airport (MAA) | Savino Del Bene / Maersk | Sea: 21–35 days; Air: 5–10 days | Best port option for bulk lab equipment; Chennai Customs has dedicated tech cargo lane |
| Pune | Pune International Airport (PNQ) or Mumbai JNPT + road | Kuehne+Nagel / UPS Supply Chain | Air: 7–12 days; Sea+Road: 25–40 days | Mumbai JNPT preferred for large equipment; road leg from Mumbai is 3–4 hours |
| Hyderabad | Rajiv Gandhi Intl Airport (HYD) | Agility Logistics / FedEx Trade Networks | Air: 6–12 days | STPI registration active in HITEC City; good customs handling for electronics |

For all prototype and development sample movements, ConglomerateIT recommends: (a) Advance licensing under India's Electronics Hardware Technology Park (EHTP) or STPI scheme to reduce import duty exposure; (b) dual-use classification review for any RF test equipment; (c) chain-of-custody documentation aligned with Client's IP protection requirements from port clearance through lab delivery.

## Lab Instrumentation Sourcing and Availability

ConglomerateIT has mapped instrumentation availability across the four cities. Key findings:

- Oscilloscopes and Probes: Tektronix and Keysight authorized distributors present in all four cities. Delivery 5–15 business days for standard models; 4–8 weeks for high-bandwidth (>1GHz) probes.

- Audio Analyzers: Audio Precision APx series available through Rhopoint Instruments India (Bengaluru office); lead time 6–8 weeks for new units; rental available through test equipment rental firms.

- RF Measurement Tools: Keysight and Rohde & Schwarz authorized service in Bengaluru and Hyderabad. Calibration certification available locally with 10–15 business day turnaround.

- Battery/Power Measurement: Keysight N6705C DC Power Analyzer available for purchase or rental in Bengaluru and Pune.

- Environmental Test Equipment: Thermal chambers available through Angelantoni (Bengaluru) and DYCOMETAL distributors; vibration test limited to partner/rental in all cities.

- Calibration and Repair: NABL-accredited calibration labs present in Bengaluru (Qualitek, TestTech), Chennai (Metrological Labs), and Hyderabad (NMR Instrumentation). Pune has limited options; recommend Bengaluru for calibration of Pune assets.

## Rented Anechoic Chamber Availability

| City | Facility / Provider | Access Model | Booking Lead Time | Limitations |
| --- | --- | --- | --- | --- |
| Bengaluru | ISRO SAC-affiliated facility (limited commercial access); National Aerospace Laboratories (NAL); Mistral Solutions private chamber; TestVerde (start-up, smaller chamber) | Rental / time-slot booking | 1–2 weeks (Mistral/TestVerde); 4–6 weeks (NAL) | NAL has access restrictions for foreign-IP products; Mistral suitable for sub-1GHz audio; no full-production-grade chamber publicly available |
| Chennai | SRM Institute of Science and Technology (limited); DSIR-certified private lab in Sriperumbudur via arrangement | Academic partnership / commercial rental | 3–4 weeks | Limited commercial scheduling; best suited for pre-compliance |
| Pune | College of Engineering Pune (CoEP) lab; Tata Motors Engineering R&D (not publicly available) | Academic partnership | 4–6 weeks | Not client-grade; prototype-level testing only |
| Hyderabad | CDAC Hyderabad (limited access); T-Hub ecosystem lab (small chamber) | Partnership / rental | 2–3 weeks | Small chamber only; full EMC chamber not currently available commercially |

ConglomerateIT's recommendation: Bengaluru (Mistral Solutions) is the most practical Day 1 option for anechoic testing. For Client-grade, production-level anechoic testing during early phases, we recommend retaining the option to use Singapore or Dubai-based facilities (1–2 day logistics) while India lab capability matures. We can connect Client with Eurofins Singapore or TUV SUD Dubai as interim options.

## EMI/RF Characterization and RF Cage Access

EMI/EMC pre-compliance and RF characterization capability is more readily available in India than full anechoic chamber access:

- Bengaluru: Mistral Solutions, CACT Bengaluru (STQC Certification), and Tektronix's RF lab partner network offer semi-anechoic rooms and RF shielded cage access. Bluetooth/OFDM characterization is available through QCC partner labs (limited to authorized partners).

- Chennai: STQC Chennai and Bureau Veritas Testing Division provide EMI pre-compliance; full RF cage available at BV Chennai facility on rental basis (booking 2–3 weeks).

- Pune: InterTek Pune provides EMC pre-compliance; RF cage available. Good option for IEC 62368 compliance testing relevant to audio products.

- Hyderabad: Limited direct EMC facility access; TUV Rheinland Hyderabad provides consulting but limited in-house RF capability.

## Lab Sequencing Recommendation

ConglomerateIT recommends the following phased lab model:

- Months 1-6 (Rented/Partner Labs): All engineering validation uses rented facilities (Mistral Bengaluru for anechoic/audio; STQC Bengaluru for EMI; partner QCC/MediaTek labs for BT characterization). No Client-owned lab investment required.

- Months 6-12 (Hybrid): Client leases dedicated lab space within Bengaluru facility. Installs Client-owned oscilloscopes, audio analyzers, and battery measurement tools. Continues to use rented anechoic and RF cage facilities externally.

- Year 2+ (Client-Owned Build-Out): Full Client-owned RF shielded room and semi-anechoic chamber within dedicated facility. Estimated build cost INR 2.5–4.5 Cr depending on specification. ConglomerateIT can connect Client with specialist lab design firms (ETS-Lindgren India partnership).

# Audio Wearable SoC Ecosystem and Partner Proximity

## BT SoC and Wireless Chip Manufacturer Proximity

| Vendor / Partner | Bengaluru | Chennai | Hyderabad | Pune |
| --- | --- | --- | --- | --- |
| Qualcomm (QCC audio BT SoC) | Present: large R&D centre, Whitefield | Present: limited | Present: significant VLSI/modem team | Limited |
| MediaTek (BT/WiFi/audio chips) | Present: audio/connectivity team | Limited | Present: growing team | Limited |
| Nordic Semiconductor | Distributor / FAE presence | None | FAE presence | FAE presence |
| Cirrus Logic (audio codecs) | Present: India engineering team | None | None | None |
| Silicon Laboratories (BT/WiFi SoC) | FAE + distributor | FAE | FAE | FAE |
| Texas Instruments (audio amplifiers) | Present: R&D centre | Present: large campus | Present | Distributor only |
| Synaptics (audio/IoT) | FAE presence | None | FAE presence | None |

## Partner Coordination Approach

ConglomerateIT recommends Client establish a formal Partner Coordination Council for India engineering covering: embedded audio and BT SoC vendors, RF characterization partners, anechoic chamber access partners, and university talent pipeline partners. We would support Client in standing up this council at Month 3 and managing the administrative coordination (NDA frameworks, access scheduling, joint roadmap reviews).

# GR&D Transition, Hiring, and Onboarding Model

## Transition Approach Overview

ConglomerateIT's GR&D India transition model is structured across three phases:

- Phase 1: Foundation (Months 1-3): Entity setup, role architecture finalized, Day 1 JDs approved, recruiting activated, lab logistics initiated, security framework deployed, development environment provisioning started.

- Phase 2: Ramp (Months 3-9): Day 1 hires onboarded and productive, partner-supported resources active, knowledge transfer (shadowing and reverse shadowing) underway, temporary lab access operational.

- Phase 3: Stabilization (Months 9-18): Partner resources evaluated for conversion, BOT cohort assessed, India team self-sufficient on defined work streams, Client-owned lab space buildout initiated.

## Knowledge Transfer and Onboarding Model

For GR&D roles, ConglomerateIT recommends:

- Shadowing: India engineer shadows counterpart engineer in Client's primary engineering hub (US/EU) for 4-6 weeks before India go-live. Travel costs are one-time and de-risk knowledge transfer significantly.

- Reverse Shadowing: Senior Client engineer visits India site for 2-3 weeks at Month 2-3 to calibrate India team's technical standards and tools usage.

- Structured Onboarding Checklist: Lab access, secure workstation provisioning, code repository access, development sample receipt, mentor assignment, and 30/60/90-day milestone sign-off.

- 30/60/90-Day Milestones: Month 1: environment setup and toolchain complete; Month 2: first code contribution reviewed and merged; Month 3: independent assigned work stream with defined deliverable.

## BOT Candidate Non-Conversion Risk Management

If a partner-supported or BOT candidate is not converted to Client due to performance, culture, technical fit, or business need changes, ConglomerateIT's standard contract includes: 30-day notice for non-conversion; ConglomerateIT absorbs re-deployment cost; IP and access revocation within 24 hours of notification; no punitive fees to Client for non-conversion during the evaluation window. Client retains the right to decline conversion at any assessment milestone without obligation.

# Engineering Security, IP, and Highly Sensitive Data Readiness

## Data and IP Protection Framework

ConglomerateIT recognizes that Client's engineering data: circuit designs, firmware source code, audio algorithms, DSP pipeline specifications, and development samples: represents core competitive IP. Our recommended controls framework for GR&D India is structured across four layers:

- Physical Security: Dedicated engineering lab space with biometric access control, CCTV coverage, clean-desk policy, locked prototype storage (key card access log), and no-external-device zones for lab areas.

- Endpoint and Device Security: Client-managed MDM on all engineering workstations, encrypted SSDs, USB port restrictions (except approved debug interfaces), and VPN-only access to Client code repositories and internal tools.

- Data Loss Prevention: DLP agents (aligned with Client's existing DLP platform) deployed on all Client-owned -managed endpoints. Email gateway scanning for technical file attachments. Cloud storage upload restrictions.

- Code Repository Governance: GitHub/GitLab with branch protection rules, signed commits, mandatory code review, and audit logging. No personal repository access from Client codebases.

## Differentiated Controls by Resource Type

| Control Area | Direct Client Hire | Partner-Supported | BOT Resource | External Contractor |
| --- | --- | --- | --- | --- |
| Code Repository Access | Full access per role | Limited: defined repo only | Scoped access; reviewed monthly | Read-only or no access |
| Development Sample Access | Full access with log | Supervised access only | Supervised, logged | No access |
| Lab Access | Full: biometric enrolment | Escorted or time-limited | Escorted, logged | No access |
| IP Assignment | Full IP assignment in employment agreement | IP assignment in SOW; ConglomerateIT warranty | Staged IP assignment at conversion | Client retains IP; contractor waives rights |

| Offboarding | Standard HR offboarding + IT revocation within 24h | Access revocation Day 1 of end of engagement | Access revocation + asset return on non-conversion | Access revocation on contract end |
| --- | --- | --- | --- | --- |
| Background Verification | Full BGV: criminal, employment, education | Full BGV via ConglomerateIT | Full BGV via ConglomerateIT | BGV per client requirement |

## Rented Facility and Partner Lab Controls

For all rented anechoic chambers, EMI/RF facilities, and partner development centre access:

- Development samples and prototypes are transported in sealed, tamper-evident packaging with chain-of-custody documentation.

- Client personnel or ConglomerateIT-designated escorts are present at all times during external lab sessions.

- No samples or engineering documents are left at external facilities between sessions.

- All external lab facilities sign a facility access NDA with Client before first use, reviewed by Client legal.

- Session logs (access time, personnel present, equipment used) are maintained and available to Client on request.

## Audit Readiness and Incident Response

ConglomerateIT maintains an audit-ready controls log for all GR&D engineering engagements, including access grant/revocation records, sample movement logs, and DLP alert histories. In the event of a suspected IP incident, our incident response protocol includes: immediate access suspension within 2 hours of detection; legal hold on relevant systems; notification to Client CISO within 4 hours; forensic support engagement within 24 hours. A full IR runbook specific to Client's engagement will be delivered as part of the Security and IP Protection deliverable.

# Required GR&D Deliverables: Delivery Commitment

| Deliverable | Contents | Delivery Timeline | Client Stakeholders |
| --- | --- | --- | --- |
| Engineering Role Architecture & Hiring Plan | Role families, JDs, hiring sequence, Day 1 vs Year 1 roles, sourcing channels, compensation bands, time to fill, attrition risk, city availability | Week 3 post-selection | GR&D Head, India HR Lead, Procurement |
| City-by-City GR&D Location Comparison | Comparative view of Bengaluru, Chennai, Pune, Hyderabad across all GR&D capabilities; includes talent heatmap | Week 4 post-selection | GR&D Head, Real Estate/Facilities |
| Lab, Instrumentation, and Sample Logistics Assessment | Port/airport routes, sample import/export process, customs, instrumentation sourcing, temporary lab access, launch dependencies | Week 4 post-selection | Engineering Operations, Legal/Compliance |
| Specialized Facilities Map | City-by-city anechoic, EMI/RF, RF cage, BT/OFDM availability; access model; cost ranges | Week 5 post-selection | GR&D Engineering Leads, Validation Team |
| Audio Wearable SoC Ecosystem Map | BTSoC/BT/WiFi vendor proximity, partner dev centres, proximity map, collaboration cadence, ecosystem gaps | Week 5 post-selection | GR&D Head, Engineering Partnerships |
| GR&D Transition, Hiring, and Onboarding Plan | Transition phases, KT plan, shadowing, lab readiness, tool access, 30/60/90-day milestones, stabilization | Week 6 post-selection | GR&D Head, India Site Lead, HR |
| Engineering Security and IP Control Plan | Controls for data, prototypes, hardware, code, lab access, DLP, encryption, access governance, IR runbook, secure offboarding | Week 6 post-selection | CISO, GR&D Head, Legal, Procurement |
| R&D Transition Case Studies | Sanitized examples of R&D GCC build-outs; client sector, role scope, timeline, outcomes, lessons, sample templates | Available on request under NDA | GR&D Head, Executive Sponsors |

# GR&D Role and Facility Response Matrix

The following matrix provides ConglomerateIT's summary city-by-city GR&D readiness assessment. Narrative explanations are provided in the questionnaire responses above.

| Capability / Role | Bengaluru | Chennai | Pune | Hyderabad |
| --- | --- | --- | --- | --- |
| Audio DSP / Ultra-Low-Latency Signal Processing talent depth | Very Strong: Dolby, Harman, Qualcomm alumni; 200+ active candidates | Moderate: TI India presence; 50–80 candidates | Moderate: 40–60 candidates; primarily automotive audio | Good: Samsung, Microsoft R&D; 80–100 candidates |
| Cadence Design Tools / HW-adjacent engineering talent | Strong: SoC vendor offices; 100+ qualified | Moderate: IC design teams at TI, Renesas | Moderate: limited audio-specific Cadence talent | Moderate: VLSI teams at Intel, Qualcomm |
| Wearable / Low-power battery operation talent | Strong: TWS startup ecosystem (Noise, boAt); 80–120 candidates | Limited: <30 candidates with wearable focus | Moderate: IoT/automotive crossover; 40–60 | Moderate: growing wearables community; 50–70 |
| Sensor integration and sensor fusion talent | Strong: IoT and consumer electronics density | Moderate: automotive ADAS adjacent | Strong: automotive ADAS; strong crossover potential | Moderate: IoT and robotics community |
| TWS audio / Bluetooth audio engineering talent | Very Strong: QCC ecosystem; 150+ candidates | Moderate: 40–60 candidates | Moderate: 30–50 candidates | Good: 70–90 candidates |
| FreeRTOS / Zephyr / Embedded Linux / embedded platform talent | Very Strong: 300+ active candidates | Good: 100–150 candidates | Strong: 150–200; automotive/industrial background | Strong: 200+ candidates; strong RTOS culture |
| TinyML / Battery-Optimized AI Inference talent | Good: IISc pipeline; 50–80 candidates; competitive market | Limited: <25 candidates; primarily academic | Moderate: 30–40 candidates | Good: IIIT Hyderabad pipeline; 50–70 candidates |
| Mobile App (iOS/Android, BT/WiFi stack, Swift, Kotlin, KMP, Flutter) | Very Strong: 500+ candidates with BT/WiFi stack experience | Good: 200–300 candidates | Strong: 300–400 candidates | Very Strong: 450+ candidates; cost advantage |
| Quickest sample/board/tool import-export route | BLR Airport: 7–14 days air; STPI recommended | MAA Airport/Port: 5–10 days air; sea option for bulk | PNQ Airport or JNPT sea: 7–12 days air | HYD Airport: 6–12 days air; STPI in HITEC City |
| Instrumentation sourcing and local calibration availability | Strong: Keysight, R&S authorized; NABL calibration available | Good: TI/Keysight distributors; NABL present | Good: InterTek; Keysight distributor; NABL present | Strong: Keysight, Rohde & Schwarz authorized; NABL present |
| Rented anechoic chamber availability | Moderate: Mistral Solutions (small); NAL (restricted access) | Limited: SRM/academic only; not commercial grade | Limited: CoEP academic; not Client-grade | Limited: T-Hub small chamber; not Client-grade |
| EMI/RF characterization and RF cage access | Good: STQC, Mistral, Tektronix RF partner labs | Good: Bureau Veritas Chennai; STQC Chennai | Good: InterTek Pune; RF cage available | Moderate: TUV Rheinland; limited in-house RF |
| Bluetooth/OFDM characterization access | Good: QCC/MediaTek partner labs (authorized access required) | Limited: no direct commercial access | Limited | Limited |
| Proximity to BTSoC/BT/WiFi chip manufacturers or partner centres | Very High: Qualcomm QCC, MediaTek, Cirrus Logic on-site | Moderate: TI India; limited BT SoC presence | Moderate: Qualcomm and TI limited presence | Good: Qualcomm, MediaTek present; smaller teams |
| Overall GR&D launch readiness rating | HIGHEST: Recommended primary anchor city | SUPPLEMENTAL: Best for sample logistics and IC design | SECONDARY: Best for RTOS/industrial crossover and Mobile App | STRONG CO-LOCATION: Best for Mobile App and RTOS cost efficiency |

# Closing Statement

ConglomerateIT is confident in our ability to support Client's India GR&D engineering enablement with the depth, specificity, and operational rigor this program requires. Our response reflects direct India delivery experience.

We look forward to the opportunity to advance to the next stage of Client's evaluation and to present our GR&D engineering capability in greater detail.

## Commercial Assumptions

The pricing framework in Section 15.1 is based on the following commercial assumptions. BOSE should review each assumption carefully and identify any deviations that would require model recalibration prior to Phase 1 confirmation.

| Assumption | Detail and Implication |
| --- | --- |
| Initial team size | Example pricing reflects 15 software engineers of mixed seniority. Actual pricing scales linearly based on confirmed headcount by role and level. Volume above 50 FTE may attract marginal cost efficiencies. |
| Primary location | Hyderabad (primary GCC hub). Bengaluru pricing is approximately 15–18% higher for equivalent roles. The confirmed city selected in Phase 1 will determine final salary and real estate benchmarks. |
| Currency and exchange rate | USD invoicing throughout. All INR-denominated costs (salaries, rent, utilities, statutory benefits) are converted to USD at the prevailing interbank rate at time of invoicing. No exchange rate lock is assumed beyond the 90-day pricing validity window. |
| Management fee structure | A flat 15% management fee is applied to the verified actual cost base (Cost + 15%). This fee is consistent across all headcount levels and aligns with India Transfer Pricing Safe Harbour guidelines for IT service exports. |
| Facilities model | Assumes temporary incubation within ConglomerateIT’s existing premises for Months 1–4 and transition to a dedicated facility from Month 5. Permanent facility costs will be confirmed following site selection in Phase 1. Model 2 (Parallel Track BOT) includes facility build costs as a separate line item. |
| Hardware and endpoints | Laptop and workstation costs are passed through at actual verified cost with zero markup. Assumes BOSE-specified standard enterprise configuration. GR&D engineering workstations may carry a higher specification and cost. |
| Travel and expenses | International travel for knowledge transfer activities, client workshops, site visits, and executive engagements is excluded from the monthly cost-plus structure and will be billed at actual cost with prior written approval. |
| Legal and tax advisory | Specialist legal and transfer pricing advisory, including Big 4 coordination for statutory registrations and intercompany agreement review, is excluded from the management fee and will be quoted as a separate professional services engagement. |
| BOT transfer / success fee | A one-time transfer fee applies if BOSE elects to execute a full legal entity and workforce transfer under the Build-Operate-Transfer model. The transfer fee will be agreed in writing prior to execution and is not included in the monthly cost-plus pricing. Asset transfer (hardware, lease novation) is at book value. |
| GR&D lab and logistics costs | Engineering lab access fees (rented anechoic chambers, EMI/RF facilities, RF cage sessions) and development sample import/export costs are passed through at actual cost with prior approval. ConglomerateIT does not apply a markup to third-party lab or logistics charges. |
| Price validity | All pricing and benchmarks in this response are valid for 90 days from the submission date (May 2026). Salary benchmarks will be refreshed at Phase 1 completion to reflect current market conditions at the confirmed city and role mix. |

ConglomerateIT | Submitted May 2026 | Confidential and Proprietary